## Revised Budget and Schedule
Milestone ( sequential view) | Task ID | Workstream | Task Name | Commencement Dependencies | Description of work to be done | Start | Finish | Working weeks in period | Hours per week avg | Project hours / units | Entity | Role | Blended rate / hour | Cost | Type | Total Project Costs
Continuous |  | Project Management | 1. Project Manager |  | Coordinate internal and external teams. Track milestones. Report on progress. Manage stakeholders. Report | 2026-06-01 | 2028-06-01 | 104.8 | 2 | 209.6 | Advisors/Consultants | Project manager | 162.5 | 34060 | Time | 10274089.56
Continuous |  | Project Management | 1. Project Manager |  | Coordinate internal and external teams. Track milestones. Report on progress. Manage stakeholders. Report | 2026-06-01 | 2028-06-01 | 104.8 | 2 | 209.6 | Advisors/Consultants | Project technical lead | 162.5 | 34060 | Time
Continuous |  | Project Management | 2. Steering committee participation |  | Provide technical oversight and direction | 2026-06-01 | 2028-06-01 | 104.8 | 1 | 104.8 | Reposit Power | CEO | 356.25 | 37335 | Time
Continuous |  | Project Management | 2. Steering committee participation |  | Provide technical oversight and direction | 2026-06-01 | 2028-06-01 | 104.8 | 1 | 104.8 | Reposit Power | CFO | 237.5 | 24890 | Time
Continuous |  | Project Management | 2. Steering committee participation |  | Provide technical oversight and direction | 2026-06-01 | 2028-06-01 | 104.8 | 1 | 104.8 | Reposit Power | CTO | 237.5 | 24890 | Time | Total Project Management Costs
Continuous |  | Project Management | 2. Steering committee participation |  | Provide technical oversight and direction | 2026-06-01 | 2028-06-01 | 104.8 | 1 | 104.8 | Ambibox | CTO | 237.5 | 24890 | Time | 24890
Continuous |  | Project Management | 2. Steering committee participation |  | Provide technical oversight and direction | 2026-06-01 | 2028-06-01 | 104.8 | 0 | 0 | Race2030 | External nil | 0 | 0 | Time
Continuous |  | Project Management | 2. Steering committee participation |  | Provide technical oversight and direction | 2026-06-01 | 2028-06-01 | 104.8 | 0 | 0 | ENA | External nil | 0 | 0 | Time
Continuous |  | Project Management | 2. Steering committee participation |  | Provide technical oversight and direction | 2026-06-01 | 2028-06-01 | 104.8 | 0 | 0 | ARENA Observer | External nil | 0 | 0 | Time
Continuous |  | Project Management | 3. Accounting (blended salary rate) |  | Reconcile and track time sheets and budgets | 2026-06-01 | 2028-06-01 | 104.8 | 2 | 209.6 | Reposit Power | Financial controller | 153 | 32068.8 | Time
Continuous |  | Project Management | 4. Authorship |  | As and when required | 2026-06-01 | 2028-06-01 | 104.8 | 0.25 | 26.2 | Reposit Power | Reporting Lead | 162.5 | 4257.5 | Time
Continuous |  | Project Management | 5. Escalation and signoff |  | As and when required | 2026-06-01 | 2028-06-01 | 104.8 | 0.25 | 26.2 | Reposit Power | CEO | 356.25 | 9333.75 | Time
1 | 1.1 | Project Initiation | 1. Kickoff meeting and technical review between key technical partners |  | Define scope of current stage | 2026-06-01 | 2026-06-06 | 1 | 4 | 4 | Reposit Power | CEO | 356.25 | 1425 | Time
1 | 1.2 | Project Initiation | 1. Kickoff meeting and technical review between key technical partners |  | Define scope of current stage | 2026-06-01 | 2026-06-06 | 1 | 4 | 4 | Reposit Power | CTO | 237.5 | 950 | Time
1 | 1.3 | Project Initiation | 1. Kickoff meeting and technical review between key technical partners |  | Define scope of current stage | 2026-06-01 | 2026-06-06 | 1 | 4 | 4 | Reposit Power | Senior Developer | 153.125 | 612.5 | Time
1 | 1.4 | Project Initiation | 1. Kickoff meeting and technical review between key technical partners |  | Define scope of current stage | 2026-06-01 | 2026-06-09 | 1.4 | 4 | 5.6 | Reposit Power | Engineering Developer | 143.75 | 805 | Time
1 | 1.5 | Project Initiation | Procure lab testing hardware & development kit. |  | Purchase and set up equipment for testing communication implementations (likely Trialog ComboS). Outcome - project initiated, standards implementation confidence, confident you can progress - testing validity of progressing at that point | 2026-06-13 | 2026-06-27 | 2 | 8 | 16 | Reposit Power | Engineering Developer | 143.75 | 2300 | Time
1 | 1.7 | Reposit Controller Hardware Enhancement | Design for new SoC to support 6-channel FCAS metering & disjunctive optimisation | 1.6 | Supports the enhanced metering, and facilitate the upgrade to OCPP2.1 | tba | tba | 20 | 80 | 1600 | LAURENCE | Blended rate | 168.75 | 270000 | Direct cost
1 | 1.8 | Hardware Communication | Finalise ISO 15188-20 specification | 1.1 | Agreeing with BEV that the standard will be implemented in a consistent way. - Progress report and lessons learnt on standards readiness, implementation and bi-directional charging feasibility |  |  | 4 | 160 | 640 | Reposit Power | Blended rate | 168.75 | 108000 | Time
1 | 1.9 | Hardware Communication | Finalise OCPP2.1 specification | 1.1 | Reposit and EVSE (bi directional charger) agreement that OCPP2.1 will be implemented consistently |  |  | 3 | 160 | 480 | Reposit Power | Blended rate | 168.75 | 81000 | Time
1 | 1.10 | Hardware Communication | Procure EVSE unit for lab testing |  | Reposit to procure the target EVSE for installation in their lab environment |  |  | 1 | 120 | 120 | Reposit Power | Blended rate | 168.75 | 20250 | Time
1 | 1.11 | Reposit Cloud Enhancement | Develop configuration tools & database structure for EVSE & Vehicle configuration |  | Build system to identify, store, and record the BEV |  |  | 5 | 160 | 800 | Reposit Power | Blended rate | 168.75 | 135000 | Time
1 | 1.12 | Digital Trust Validation | Wireframe PKI specification agreed | 1.1 | Agreement on the implementation of security certificate for BEV OEM (car supplier)and EVSE (car charger) |  |  | 6 | 160 | 960 | Reposit Power | Blended rate | 168.75 | 162000 | Time
1 | 1.13 | Market Integration | Engage with DNSPs on connection approval requirements | 1.1 | Confirm DNSP bidirectional charger application process and requirements |  |  | 6 | 120 | 720 | Reposit Power | Blended rate | 168.75 | 121500 | Time
2 | 2.14 | Reposit Controller Software Enhancement | Develop bidirectional EVSE decision-making capabilities |  | Develop bidirectional charging capability within the Reposit controller |  |  | 16 | 200 | 3200 | Reposit Power | Blended rate | 168.75 | 540000 | Time
2 | 2.15 | Customer Product Development | Identify existing Reposit customers with potentially compatible vehicles | 1.1 | Potential customer identification within reposit existing customers - requires that they have eligible cars |  |  | 2 | 120 | 240 | Reposit Power | Blended rate | 168.75 | 40500 | Time
2 | 2.16 | Hardware Communication | OCPP 2.1 server implemented on Reposit Controller | 1.9 | Standard implemented on Reposit controller |  |  | 16 | 200 | 3200 | Reposit Power | Blended rate | 168.75 | 540000 | Time
2 | 2.17 | Hardware Communication | OCPP 2.1 client on EVSE | 1.9 | Standard implemented on Car charger. (- can a reposit controller send charge and discharge signals, and receive state of charge in test environment) |  |  | 14 | 200 | 2800 | Reposit Power | Blended rate | 168.75 | 472500 | Time
2 | 2.18 | Hardware Communication | Test vehicle and EVSE ISO 15118-20 Communication | 1.8 | Test standard implemented successfully. ("- Progress report, lessons learnt and success of hardware upgrade implementations ANd necessary updates on initially agreed specifications") |  |  | 6 | 200 | 1200 | Reposit Power | Blended rate | 168.75 | 202500 | Time
2 | 2.19 | Reposit Controller Software Enhancement | Control Schema for EVSE Implemented | 2.16 | Reposit controller capable of sending car charger charge or discharge signals, and receive state of charge from BEV |  |  | 14 | 200 | 2800 | Reposit Power | Blended rate | 168.75 | 472500 | Time
2 | 2.20 | Hardware Communication | Test end-to-end telemetry from Reposit controller to BEV (notional - actual or mock BEV device) | 2.16, 2.17, 1.10 | Communications test for hardware |  |  | 6 | 160 | 960 | Reposit Power | Blended rate | 168.75 | 162000 | Time
2 | 2.21 | Customer Product Development | Identify test vehicle (BYD provided, lent or acquired) | 2.2 | Determine how Reposit will access an appropriate BEV to complete demonstration test in Milestone 3 |  |  | 2 | 80 | 160 | Reposit Power | Blended rate | 168.75 | 27000 | Time
| . | [8 empty] | 0 | Reposit Power | Blended rate | 168.75 | 0 | Time
3 | 3.22 | Vehicle Offering Finalisation | Vehicle OEM provides test vehicle(s) and/or firmware version for testing | 2.21 | Acquire vehicle for testing. - using test vehicle to ensure that the system is fully operational, standards are implemented and functional, and reposit system and app are ready for BEV customers |  |  | 1 | 8 | 8 | Reposit Power | Blended rate | 168.75 | 1350 | Time
3 | 3.23 | Hardware Communication | Test end-to-end power setpoint response from controller through to vehicle | 3.22 | Test of system response time, which will inform what grid and system services can be delivered. - Preparing the technology for the demonstration project |  |  | 8 | 160 | 1280 | Reposit Power | Blended rate | 168.75 | 216000 | Time
3 | 3.24 | Customer Product Development | Draft customer value proposition for initial No Bill product | 2.15 | Develop product for the customer offering |  |  | 6 | 160 | 960 | Reposit Power | Blended rate | 168.75 | 162000 | Time
3 | 3.25 | Customer Product Development | Test notional product with prospective customers to validate uptake potential | 3.24 | Socialise product offering with customers and determine attractiveness |  |  | 6 | 160 | 960 | Reposit Power | Blended rate | 168.75 | 162000 | Time
3 | 3.26 | Customer Product Development | Add key controls (i.e overrides) and data displays to Reposit app |  | Enhance existing Reposit app to include key BEV features, i.e override and BEV data displays |  |  | 8 | 160 | 1280 | Reposit Power | Blended rate | 168.75 | 216000 | Time
3 | 3.27 | Customer Product Development | In-App Customer Feedback engine |  |  |  |  | 2 | 1 | 2 | Reposit Power | Senior Developer | 153.125 | 306.25 | Time
3 | 3.28 | Reposit Controller Hardware Enhancement | Finalise upgraded controller specifications and manufacture prototypes | 1.7 |  |  |  | 40 | 200 | 8000 | LAURENCE | Blended rate | 168.75 | 1350000 | Direct cost
3 | 3.29 | Market Integration | Identify FCAS services which can be delivered via V2G | 3.23 |  |  |  | 4 | 120 | 480 | Reposit Power | Blended rate | 168.75 | 81000 | Time
3 | 3.30 | Reposit Controller Software Enhancement | Enhance frequency response control to enable V2G FCAS delivery | 3.29 | Upgrade reposit controller to enable FCAS response from BEV |  |  | 10 | 80 | 800 | Reposit Power | Blended rate | 168.75 | 135000 | Time
3 | 3.31 | Reposit Controller Software Enhancement | Develop EV forecast engine (predict connectivity, energy needed for mobility) | 1.11 | Build a forecast engine to be able to predict BEV availability and state of charge |  |  | 12 | 160 | 1920 | Reposit Power | Blended rate | 168.75 | 324000 | Time
3 | 3.32 | Reposit Controller Software Enhancement | Implement new vehicle & EVSE metric collection and publication to cloud | 3.23 | Develop ability to collect information from EVSE (Car charger) and BEV (car) and store on Reposit's cloud |  |  | 6 | 120 | 720 | Reposit Power | Blended rate | 168.75 | 121500 | Time
3 | 3.33 | Customer Product Development | End-to-end test from Reposit App, through to test vehicle | 3.32 | Full test of end to end system functionality on test vehicle |  |  | 4 | 120 | 480 | Reposit Power | Blended rate | 168.75 | 81000 | Time
4 | 4.34 | Vehicle Offering Finalisation | Vehicle OEM produces warranty terms or waivers specifically covering vehicles used within the project | 3.22 | - Acquiring 5 customers (Gen 1), get warranty waivers, develop and execute customer terms and conditions, de |  |  | 3 | 60 | 180 | Reposit Power | Blended rate | 168.75 | 30375 | Time
4 | 4.35 | Customer Product Development | Employ & on-board customer concierge | 3.24 |  |  |  | 52 | 40 | 2080 | Reposit Power | Blended rate | 168.75 | 351000 | Time
4 | 4.36 | Customer Product Development | T&C legal review | 3.24 |  |  |  | 2 | 40 | 80 | Reposit Power | Blended rate | 168.75 | 13500 | Direct cost
4 | 4.37 | Customer Product Development | Finalise customer V2G product within project | 4.36 |  |  |  | 6 | 80 | 480 | Reposit Power | Blended rate | 168.75 | 81000 | Time
4 | 4.38 | Customer Product Development | Release updated Reposit App with EVSE+Vehicle support | 3.33 | Update Reposit App to enable BEV integration |  |  | 8 | 120 | 960 | Reposit Power | Blended rate | 168.75 | 162000 | Time
4 | 4.39 | Customer Product Development | Learning Centre expansion & Customer Support Training | 4.37 | Develop and publish educational articles for Deposits learning center, and support guides for customer support team |  |  | 5 | 80 | 400 | Reposit Power | Blended rate | 168.75 | 67500 | Time
4 | 4.40 | Product Deployment | Produce installation instructions, safety guidelines and other key material for installers | 3.23 | Develop how-to guides for installers to ensure compliance and full functionality |  |  | 4 | 60 | 240 | Reposit Power | Blended rate | 168.75 | 40500 | Time
4 | 4.41 | Product Deployment | Procure EVSE for customer installations | 4.37 | Purchase EVSE units for customer installs |  |  | 2 | 40 | 80 | Reposit Power | Blended rate | 168.75 | 13500 | Time
4 | 4.42 | Customer Recruitment Marketing | Create and deploy marketing to identify customers for trial | 4.37 | Begin customer acquisition marketing |  |  | 4 | 60 | 240 | Reposit Power | Blended rate | 168.75 | 40500 | Time
4 | 4.43 | Customer Recruitment Marketing | Recruit Gen1 customers | 4.42 | Identify minimum of 5 customers to participate in the demonstration project (Gen1) |  |  | 3 | 40 | 120 | Reposit Power | Blended rate | 168.75 | 20250 | Time
4 | 4.44 | Market Integration | Get DNSP approvals for Gen1 customer installations | 1.13 | Gain DNSP connection approval for bidirectional chargers |  |  | 2 | 40 | 80 | Reposit Power | Blended rate | 168.75 | 13500 | Time
5 | 5.45 | Product Deployment | Identify first 1 or 2 flagship install sites, and install with oversight and review | 4.44 | Complete installations at initial Gen 1 sites (1 or 2), with heavy oversight to ensure installation is compliance and correct. Initialise and finalise preparation for demonstration trial |  |  | 5 | 80 | 400 | Reposit Power | Blended rate | 168.75 | 67500 | Time
5 | 5.46 | Product Deployment | Proceed with installation at rest of Gen1 customer sites | 5.45 | Complete remaining installations using any learnings from the initial installation sites |  |  | 4 | 80 | 320 | Reposit Power | Blended rate | 168.75 | 54000 | Time
5 | 5.45 | Social Research | Use app feedback system and interviews to gather customer experience and sentiment data | 5.45 | After installation is complete, and before cars are utilised, gather customer feedback via social research, and in-app features including override button and real time feedback |  |  | 3 | 60 | 180 | Reposit Power | Blended rate | 168.75 | 30375 | Time
5 | 5.47 | Digital Trust Validation | Internal review of PKI identification and security | 4.43 | Verify security certificate system is functional |  |  | 2 | 40 | 80 | Reposit Power | Blended rate | 168.75 | 13500 | Time
5 | 5.45 | Market Integration | Pass AEMO performance validations, register Gen1 V2G EVSE into FCAS Dispatchable Unit | 5.45 | Enable enrollment in AEMO systems for FCAS |  |  | 4 | 80 | 320 | Reposit Power | Blended rate | 168.75 | 54000 | Time
5 | 5.48 | Market Integration | Enable 5-minute spot price response on Gen1 sites | 5.46 | Ensure that the Gen1 sites are capable to participate in 5-minute spot price trading. Conduct demonstration trial |  |  | 3 | 60 | 180 | Reposit Power | Blended rate | 168.75 | 30375 | Time
5 | 5.45 | Market Integration | Enable dynamic network price response where supported on Gen1 sites. | 5.46 | Where a customer DNSP supports Dynamic Network Prices (i.e Project Edith), V2G chargers will begin responding to these. |  |  | 3 | 60 | 180 | Reposit Power | Blended rate | 168.75 | 30375 | Time
5 | 5.49 | Digital Trust Validation | Penetration testing by 3rd party | 5.47 | Testing to verify the robust implementation of cyber security measures |  |  | 2 | 40 | 80 | External | Blended rate | 168.75 | 13500 | Direct cost
5 | 5.45 | Market Integration | Add Gen1 customers to RERT and/or MSL DUIDs | 5.46 | Ensuring Gen 1 customers can participate in RERT and Minimum system demand events |  |  | 2 | 40 | 80 | Reposit Power | Blended rate | 168.75 | 13500 | Time
6 | 6.46 | Customer Product Development | Develop & finalise experimental design for validating V2G No Bill product | 5.45 | Develop a 6 month demonstration project trial plan |  |  | 4 | 80 | 320 | Reposit Power | Blended rate | 168.75 | 54000 | Time
6 | 6.47 | Customer Product Development | Gather operational data from Gen1 sites over 6 months | 5.46 | Implement the 6 month trial plan - operational of BEV to test response, availability and customer sentiment |  |  | 26 | 60 | 1560 | Reposit Power | Blended rate | 168.75 | 263250 | Time
6 | 6.48 | Data Collection and Reporting | Produce key data pack (raw data points, overviews of market participation) | 6.47 | Collect and store demonstration project data |  |  | 3 | 60 | 180 | Reposit Power | Blended rate | 168.75 | 30375 | Time
6 | 6.49 | Data Collection and Reporting | Customer Experience Research/Feedback gathering | 4.43 | Collect and compile customer experience feedback during and at conclusion of the project. Data from trial, customer journey and experience, performance reporting, cyber security reporting, lessons learnt and recommendations, including investment decision |  |  | 4 | 80 | 320 | Reposit Power | Blended rate | 168.75 | 54000 | Direct cost
6 | 6.50 | Data Collection and Reporting | Reposit to reach determination on ongoing No Bill V2G offering | 6.47 | Reposit to make investment decision on full product offering of No Bill V2G. |  |  | 2 | 40 | 80 | Reposit Power | Blended rate | 168.75 | 13500 | Time
6 | 6.51 | Data Collection and Reporting | Digital Trust Report, including pentesting results | 5.49 | Compile cyber security report, including recommendations |  |  | 3 | 60 | 180 | Reposit Power | Blended rate | 168.75 | 30375 | Direct cost
6 | 6.52 | Data Collection and Reporting | Produce recommendations report on lessons learnt and advice to industry | 6.47 | Compile lessons learnt and recommendations report |  |  | 30 | 60 | 1800 | Reposit Power | Blended rate | 168.75 | 303750 | Direct cost
other |  | Content development |  |  | Learning Centre content about V2G, V2G in No Bill, V2G EVSE unit and install info, impacts on specific cars [warranty, safety, app, etc, etc] - Comms person - $1k/day - 10 days | 2027-06-01 | 2027-06-11 | 1.8 | 40 | 72 | Reposit | CX designer | 143.75 | 10350 | Time
other |  | Customer Journey |  |  | Customer Journey design to include the the V2G product option - Service Designer - $2k/day - 5 days | 2027-06-01 | 2027-06-11 | 1.8 | 40 | 72 | Reposit | CX designer | 143.75 | 10350 | Time
other |  | Customer Journey |  |  | Customer Journey implementation and testing to include the the V2G product option - Revenue Ops Engineer - $1k/day - 5 days | 2027-06-01 | 2027-06-06 | 0.8 | 40 | 32 | Reposit | CX designer | 143.75 | 4600 | Time
other |  | Customer Application |  |  | Customer App changes to include V2G storage - Senior Developer - $1.5k/day - 20 days | 2027-06-06 | 2027-06-27 | 3 | 40 | 120 | Reposit | Senior Developer | 153.125 | 18375 | Time
other |  | Fleet costs |  |  | Fleet management system changes to incorporate V2G EVSE + Car Models - $1.5k/day - 15 days | 2027-07-01 | 2027-07-15 | 2.2 | 40 | 88 | Reposit | Senior Developer | 153.125 | 13475 | Time
other |  | Hardware development |  |  | Trialog ComboCS with OCPP + ISO 15118-20 |  |  |  |  | 1 |  |  | 34807.5 | 34807.5 | Direct Cost
other |  | Hardware development |  |  | Starcharge Halo 7.4kW (single phase) |  |  |  |  | 5 |  |  | 7000 | 35000 | Direct Cost |  | Customers to pay the bulk, but we probably need to subsidise a bit, and at least 1 or two of these will be "lab" installs, so not customer-bought. Will be between 30 and 50 in the end
other |  | Hardware development |  |  | (maybe) Starcharge Halo 11kW (three phase) |  |  |  |  | 5 |  |  | 10000 | 50000 | Direct Cost |  | Not currently available/being homologated for Australia, but possibly available when installs commence. Price is a guesstimate. Preferred to the single phase for FCAS performance.
other |  | Hardware development |  |  | (maybe) Lab Test Vehicle |  |  |  |  | 1 |  |  | 25000 | 25000 | Direct Cost |  | In case we do need to test on a non-consumer vehicle, we'll likely pick up an Atto 1 for $25k incl all costs
other |  | Hardware development |  |  | Versinetic OCPP2.1 Licenses |  |  |  |  | 1 |  |  | 30000 | 30000 | Direct Cost |  | No idea what Versinetic will charge.
other |  | Develop and publish educational articles | for Reposits learning center, and support guides for customer support team |  | AEMO PMS (FCAS) Registration Fee |  |  |  |  | 1 |  |  | 3000 | 3000 | Direct Cost
|  | Innovation & Discovery Buffer | Scoping, planning retro, recalibrations. Unknown unknowns | [10 empty] | 1712348.26 | Time
Formulas:
Working weeks in period = INT(NETWORKDAYS([Start],[Finish]))/5

## Gantt_RW
[6 empty] | Milestone | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
Milestone | Milestone Task | Task ID | Workstream | Task Name | Dependencies | Duration (Wks) | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52 | W53 | W54 | W55 | W56 | W57 | W58 | W59 | W60 | W61 | W62 | W63 | W64 | W65 | W66 | W67 | W68 | W69 | W70 | W71 | W72 | W73 | W74 | W75 | W76 | W77 | W78 | W79 | W80 | W81 | W82 | W83 | W84 | W85 | W86 | W87 | W88 | W89 | W90 | W91 | W92 | W93 | W94 | W95 | W96 | W97 | W98 | W99 | W100 | W101 | W102 | W103 | W104 | W105 | W106 | W107 | W108 | W109 | W110 | W111 | W112 | W113 | W114 | W115 | W116 | W117 | W118 | W119 | W120 | W121 | W122 | W123 | W124 | W125 | W126 | W127
1 | 1 | 1.1 | Project Initiation | 1. Kickoff meeting and technical review between key technical partners |  | 1 | W1: 1.1
1 | 2 | 1.2 | Project Initiation | Procure lab testing hardware & development kit. |  | 2 | W1: 1.5
1 | 3 | 1.3 | Reposit Controller Hardware Enhancement | Design for three additional FCAS-compliant metering channels |  | 1 | W1: 1.6
1 | 4 | 1.4 | Reposit Controller Hardware Enhancement | Design for new SoC to support 6-channel FCAS metering & disjunctive optimisation | 1.3 | 1 | W2: 1.7
1 | 5 | 1.5 | Hardware Communication | Finalise ISO 15188-20 specification | 1.1 | 4 | W2: 1.8
1 | 6 | 1.6 | Hardware Communication | Finalise OCPP2.1 specification | 1.1 | 3 | W2: 1.9
1 | 7 | 1.7 | Hardware Communication | Procure EVSE unit for lab testing |  | 1 | W1: 1.1
1 | 8 | 1.8 | Reposit Cloud Enhancement | Develop configuration tools & database structure for EVSE & Vehicle configuration |  | 5 | W1: 1.11
1 | 9 | 1.9 | Digital Trust Validation | Wireframe PKI specification agreed | 1.1 | 6 | W2: 1.12
1 | 10 | 1.10 | Market Integration | Engage with DNSPs on connection approval requirements | 1.1 | 6 | W2: 1.13
2 | 11 | 2.11 | Reposit Controller Software Enhancement | Develop bidirectional EVSE decision-making capabilities |  | 16 | W8: 2.14
2 | 12 | 2.12 | Customer Product Development | Identify existing Reposit customers with potentially compatible vehicles | 1.1 | 2 | W9: 2.15
2 | 13 | 2.13 | Hardware Communication | OCPP 2.1 server implemented on Reposit Controller | 1.6 | 16 | W12: 2.16
2 | 14 | 2.14 | Hardware Communication | OCPP 2.1 client on EVSE | 1.6 | 14 | W12: 2.17
2 | 15 | 2.15 | Hardware Communication | Test vehicle and EVSE ISO 15118-20 Communication | 1.5 | 6 | W13: 2.18
2 | 16 | 2.16 | Reposit Controller Software Enhancement | Control Schema for EVSE Implemented | 2.13 | 14 | W28: 2.19
2 | 17 | 2.17 | Hardware Communication | Test end-to-end telemetry from Reposit controller to BEV (notional - actual or mock BEV device) | 2.13, 2.14, 1.7 | 6 | W28: 2.2
2 | 18 | 2.18 | Customer Product Development | Identify test vehicle (BYD provided, lent or acquired) | 2.17 | 2 | W8: 2.21
3 | 19 | 3.19 | Hardware Communication | Test end-to-end power setpoint response from controller through to vehicle | 3.19 | 8 | W45: 3.23
3 | 20 | 3.20 | Customer Product Development | Draft customer value proposition for initial No Bill product | 2.12 | 6 | W45: 3.24
3 | 21 | 3.21 | Customer Product Development | Test notional product with prospective customers to validate uptake potential | 3.21 | 6 | W51: 3.25
3 | 22 | 3.22 | Customer Product Development | Add key controls (i.e overrides) and data displays to Reposit app |  | 8 | W42: 3.26
3 | 23 | 3.23 | Customer Product Development | In-App Customer Feedback engine |  | 2 | W42: 3.27
3 | 24 | 3.24 | Reposit Controller Hardware Enhancement | Finalise upgraded controller specifications and manufacture prototypes | 1.4 | 20 | W44: 3.28
3 | 25 | 3.25 | Market Integration | Identify FCAS services which can be delivered via V2G | 3.20 | 4 | W53: 3.29
3 | 26 | 3.26 | Reposit Controller Software Enhancement | Enhance frequency response control to enable V2G FCAS delivery | 3.26 | 10 | W57: 3.3
3 | 27 | 3.27 | Reposit Controller Software Enhancement | Develop EV forecast engine (predict connectivity, energy needed for mobility) | 1.8 | 12 | W47: 3.31
3 | 28 | 3.28 | Reposit Controller Software Enhancement | Implement new vehicle & EVSE metric collection and publication to cloud | 3.20 | 6 | W53: 3.32
3 | 29 | 3.29 | Customer Product Development | End-to-end test from Reposit App, through to test vehicle | 3.29 | 4 | W59: 3.33
4 | 30 | 4.30 | Customer Product Development | Employ & on-board customer concierge | 3.21 | 12 | W69: 4.35
4 | 31 | 4.31 | Customer Product Development | T&C legal review | 3.21 | 2 | W69: 4.36
4 | 32 | 4.32 | Customer Product Development | Finalise customer V2G product within project | 4.33 | 6 | W71: 4.37
4 | 33 | 4.33 | Customer Product Development | Release updated Reposit App with EVSE+Vehicle support | 3.30 | 8 | W81: 4.38
4 | 34 | 4.34 | Customer Product Development | Learning Centre expansion & Customer Support Training | 4.34 | 5 | W77: 4.39
4 | 35 | 4.35 | Product Deployment | Produce installation instructions, safety guidelines and other key material for installers | 3.20 | 4 | W71: 4.4
4 | 36 | 4.36 | Product Deployment | Procure EVSE for customer installations | 4.34 | 2 | W77: 4.41
4 | 37 | 4.37 | Customer Recruitment Marketing | Create and deploy marketing to identify customers for trial | 4.34 | 4 | W77: 4.42
4 | 38 | 4.38 | Customer Recruitment Marketing | Recruit Gen1 customers | 4.39 | 3 | W81: 4.43
4 | 39 | 4.39 | Market Integration | Get DNSP approvals for Gen1 customer installations | 1.10 | 2 | W67: 4.44
5 | 40 | 5.40 | Market Integration | Add Gen1 customers to RERT and/or MSL DUIDs | 5.46 | 2 | W89: 5.45
5 | 41 | 5.41 | Product Deployment | Proceed with installation at rest of Gen1 customer sites | 5.42 | 4 | W89: 5.46
5 | 42 | 5.42 | Digital Trust Validation | Internal review of PKI identification and security | 4.40 | 2 | W93: 5.47
5 | 43 | 5.43 | Market Integration | Enable 5-minute spot price response on Gen1 sites | 5.43 | 3 | W89: 5.48
5 | 44 | 5.44 | Digital Trust Validation | Penetration testing by 3rd party | 5.44 | 2 | W95: 5.49
6 | 45 | 6.45 | Customer Product Development | Develop & finalise experimental design for validating V2G No Bill product | 5.42 | 4 | W97: 6.46
6 | 46 | 6.46 | Customer Product Development | Gather operational data from Gen1 sites over 6 months | 5.43 | 26 | W97: 6.47
6 | 47 | 6.47 | Data Collection and Reporting | Produce key data pack (raw data points, overviews of market participation) | 6.43 | 3 | W97: 6.48
6 | 48 | 6.48 | Data Collection and Reporting | Customer Experience Research/Feedback gathering | 4.40 | 4 | W121: 6.49
6 | 49 | 6.49 | Data Collection and Reporting | Reposit to reach determination on ongoing No Bill V2G offering | 6.43 | 2 | W97: 6.5
6 | 50 | 6.50 | Data Collection and Reporting | Digital Trust Report, including pentesting results | 5.46 | 3 | W125: 6.51
6 | 51 | 6.51 | Data Collection and Reporting | Produce recommendations report on lessons learnt and advice to industry | 6.43 | 30 | W97: 6.52
3 | 22 |  | Vehicle Offering Finalisation | Vehicle OEM provides test vehicle(s) and/or firmware version for testing | 2.21 | 1 | W44: 3.22
4 | 34 |  | Vehicle Offering Finalisation | Vehicle OEM produces warranty terms or waivers specifically covering vehicles used within the project | 3.22 | 3 | W67: 4.34

## Financial Model
Period | Quarter | Paid in Capital | Arena Matching | Paid in Capital | Quarterly hurdle | Cumulative hurdle | Total Hurdle at TIME n | Customer Numbers | V2G Revenues | Direct V2g Costs | Cumulative EBIT | NOPAT - 7 year losses carried so irrelevent | ROIC Qaurterly | EV Energy Cost Work Up
[14 empty] | Average Vehicle battery capacity | 70 | Kilowatt hours | INPUT CELLS
Capital dev | Q1 | 1636571.767 | 818285.8835 | 818285.8835 | 0 | 0 | 818285.8835 | 0 | 0 | 0 | -818285.8835 | 0 |  | Average mileage p/a | 17500 | Kilometeres
Capital dev | Q2 | 1645586.897 | 822793.4487 | 822793.4487 | 21630.0185 | 21630.0185 | 1662709.351 | 0 | 0 | 0 | -1662709.351 | 0 |  | Average discharge economy | 0.18 | kWh/km
Capital dev | Q3 | 733667.5643 | 366833.7822 | 366833.7822 | 21749.1685 | 43379.187 | 2072922.32 | 0 | 0 | 0 | -2072922.32 | 0 |  | Average EV Energy Usage p/a | 3150 | kW used p/a
Capital dev | Q4 | 1810269.123 | 905134.5613 | 905134.5613 | 9696.6374 | 53075.8244 | 3031132.706 | 0 | 0 | 0 | -3031132.706 | 0 |  | Average cost / KW to charge | 0.25 | AUD |  | Average Retail Tarrif
Capital dev | Q5 | 1727741.792 | 863870.8961 | 863870.8961 | 23925.7181 | 77001.5425 | 3972005.144 | 0 | 0 | 0 | -3972005.144 | 0 |  | Total cost to charge | 787.5 | AUD
Capital dev | Q6 | 629604.6975 | 314802.3488 | 314802.3488 | 22834.9821 | 99836.5246 | 4386644.018 | 0 | 0 | 0 | -4386644.018 | 0
Capital dev | Q7 | 472141.149 | 236070.5745 | 236070.5745 | 8321.2735 | 108157.7981 | 4730872.39 | 0 | 0 | 0 | -4730872.39 | 0 |  | Ev Revenue Work Up
Capital dev | Q8 | 368078.2822 | 184039.1411 | 184039.1411 | 6240.1307 | 114397.9288 | 5029309.46 | 0 | 0 | 0 | -5029309.46 | 0 |  | Average Vehicle battery capacity | 70 | Kilowatt hours | INPUT CELLS
Capital dev | Q9 | 322893.09 | 161446.545 | 161446.545 | 4864.7668 | 119262.6957 | 5310018.701 | 0 | 0 | 0 | -5310018.701 | 0 |  | Usable export energy | 15 | kWh
Capital dev | Q10 | 277707.8978 | 138853.9489 | 138853.9489 | 4267.5694 | 123530.265 | 5572402.915 | 0 | 0 | 0 | -5572402.915 | 0 |  | Window of expected use per day | 2 | Hours
Commercialisation | Q11 | 5572402.915 | 0 | 5572402.915 | 147297.1498 |  | 5719700.065 | 100 | 251212.5 | 105750 | -5574237.565 | 0 | 0% | Rate limit of charger | 7 | kW
Commercialisation | Q12 | 5719700.065 | 0 | 5719700.065 | 147297.1498 |  | 5866997.214 | 210 | 527546.25 | 222075 | -5561525.964 | 0 | 0% | Available trading energy per trading day | 14 | kWh per day window
Commercialisation | Q13 | 5866997.214 | 0 | 5866997.214 | 151190.7036 |  | 6018187.918 | 331 | 831513.375 | 350032.5 | -5536707.043 | 0 | 0% | Number of day windows | 11 | 6 days in w, 2 summer
Commercialisation | Q14 | 6018187.918 | 0 | 6018187.918 | 155084.2573 |  | 6173272.175 | 464.1 | 1165877.213 | 490785.75 | -5498180.713 | 0 | 0% | Export rate per day ( net off refill; arbitrage) | 21.75 | AUD /kWh |  | VOLL price ( market cap price - what can we rely on, what do we model here?
Commercialisation | Q15 | 6173272.175 | 0 | 6173272.175 | 159080.7307 |  | 6332352.906 | 610.51 | 1533677.434 | 645614.325 | -5444289.797 | 0 | 0% | Total revenue from just WholeSale | 2512.125 | AUD | RESULT CELL
Commercialisation | Q16 | 6332352.906 | 0 | 6332352.906 | 163180.1236 |  | 6495533.03 | 771.561 | 1938257.677 | 815925.7575 | -5373201.11 | 0 | 0%
Commercialisation | Q17 | 6495533.03 | 0 | 6495533.03 | 167385.1566 |  | 6662918.186 | 948.7171 | 2383295.945 | 1003268.333 | -5282890.575 | 0 | 0% | Wholesale Trading Margin | 1724.625
Commercialisation | Q18 | 6662918.186 | 0 | 6662918.186 | 171698.5502 |  | 6834616.736 | 1143.5888 | 2872838.039 | 1209345.167 | -5171123.864 | 0 | 0% | FCAS | 0 |  |  | What do we assume?
Commercialisation | Q19 | 6834616.736 | 0 | 6834616.736 | 176123.0968 |  | 7010739.833 | 1357.9477 | 3411334.343 | 1436029.683 | -5035435.173 | 0 | 0% | MSL | 0 |  |  | What do we assume?
Commercialisation | Q20 | 7010739.833 | 0 | 7010739.833 | 180661.6608 |  | 7191401.494 | 1593.7425 | 4003680.278 | 1685382.652 | -4873103.868 | 0 | 0%
Commercialisation | Q21 | 7191401.494 | 0 | 7191401.494 | 185317.1803 |  | 7376718.674 | 1853.1167 | 4655260.805 | 1959670.917 | -4681128.786 | 0 | 0%
Commercialisation | Q22 | 7376718.674 | 0 | 7376718.674 | 190092.6691 |  | 7566811.343 | 2138.4284 | 5371999.386 | 2261388.008 | -4456199.966 | 0 | 0% | Revenue Builder p/a
Commercialisation | Q23 | 7566811.343 | 0 | 7566811.343 | 194991.2187 |  | 7761802.562 | 2452.2712 | 6160411.824 | 2593276.809 | -4194667.547 | 0 | 0% | Cost to Acquire | 250 |  |  | Low side
Commercialisation | Q24 | 7761802.562 | 0 | 7761802.562 | 200016.0005 |  | 7961818.563 | 2797.4983 | 7027665.507 | 2958354.49 | -3892507.546 | 0 | 0% | Cost to Serve | 20
Commercialisation | Q25 | 7961818.563 | 0 | 7961818.563 | 210457.3556 |  | 8172275.918 | 3177.2482 | 7981644.558 | 3359939.939 | -3550571.3 | 0 | 0% | Revenue per customer | 2512.125
Commercialisation | Q26 | 8172275.918 | 0 | 8172275.918 | 210457.3556 |  | 8382733.274 | 3594.973 | 9031021.513 | 3801683.933 | -3153395.693 | 0 | 0% | Cost per customer | 1057.5
Commercialisation | Q27 | 8382733.274 | 0 | 8382733.274 | 216020.4437 |  | 8598753.717 | 4054.4703 | 10185336.16 | 4287602.326 | -2701019.879 | 0 | 0% | Growth Metrics
Commercialisation | Q28 | 8598753.717 | 0 | 8598753.717 | 221583.5319 |  | 8820337.249 | 4559.9173 | 11455082.28 | 4822112.559 | -2187367.527 | 0 | 0% | Quarterly customer | 100 | INPUT CELLS
Commercialisation | Q29 | 8820337.249 | 0 | 8820337.249 | 227293.6709 |  | 9047630.92 | 5115.909 | 12851803.01 | 5410073.815 | -1605901.726 | 0 | 0% | Quarterly growth rate net ( inludes any attrition) | 10%
Commercialisation | Q30 | 9047630.92 | 0 | 9047630.92 | 233150.8609 |  | 9280781.781 | 5727.4999 | 14388195.81 | 6056831.196 | -949417.1673 | 0 | 0% | Dampening effect of fleet avaialbility | 25% |  |  | 1 in four cars wont be plugged in during a VOLL event
Commercialisation | Q31 | 9280781.781 | 0 | 9280781.781 | 239158.9889 |  | 9519940.77 | 6400.2499 | 16078227.89 | 6768264.316 | -209977.1949 | 0 | 0%
Commercialisation | Q32 | 9519940.77 | 0 | 9519940.77 | 245321.9419 |  | 9765262.712 | 7140.2749 | 17937263.18 | 7550840.748 | 621159.7207 | 434811.8045 | 4.453%
Commercialisation | Q33 | 9765262.712 | 0 | 9765262.712 | 251643.7098 |  | 10016906.42 | 7954.3024 | 19982202 | 8411674.822 | 1553620.754 | 1087534.528 | 10.86% | Economic metrics
Commercialisation | Q34 | 10016906.42 | 0 | 10016906.42 | 258128.3849 |  | 10275034.81 | 8849.7327 | 22231634.7 | 9358592.305 | 2598007.587 | 1818605.311 | 17.7% | Tax rate | 30% | INPUT CELLS
Commercialisation | Q35 | 10275034.81 | 0 | 10275034.81 | 264780.1655 |  | 10539814.97 | 9834.7059 | 24706010.67 | 10400201.54 | 3765994.161 | 2636195.913 | 25.01% | Hurdle rate | 11%
Commercialisation | Q36 | 10539814.97 | 0 | 10539814.97 | 271603.3575 |  | 10811418.33 | 10918.1765 | 27427824.23 | 11545971.69 | 5070434.217 | 3549303.952 | 32.83% | Arena matching | 50%
Commercialisation | Q37 | 10811418.33 | 0 | 10811418.33 | 278602.3783 |  | 11090020.71 | 12109.9942 | 30421819.16 | 12806318.86 | 6525479.593 | 4567835.715 | 41.19% | CLEARS 11% HURDLE | 4.453% | RESULT CELL
Commercialisation | Q38 | 11090020.71 | 0 | 11090020.71 | 285781.7587 |  | 11375802.47 | 13420.9936 | 33715213.57 | 14192700.74 | 8146710.364 | 5702697.255 | 50.13%
Commercialisation | Q39 | 11375802.47 | 0 | 11375802.47 | 300700.3093 |  | 11676502.78 | 14863.093 | 37337947.43 | 15717720.82 | 9943723.838 | 6960606.687 | 59.61%
Commercialisation | Q40 | 11676502.78 | 0 | 11676502.78 | 300700.3093 |  | 11977203.09 | 16449.4023 | 41322954.67 | 17395242.9 | 11950508.69 | 8365356.083 | 69.84%
Commercialisation | Q41 | 11977203.09 | 0 | 11977203.09 | 308648.819 |  | 12285851.9 | 18194.3425 | 45706462.64 | 19240517.19 | 14180093.55 | 9926065.484 | 80.79%
Commercialisation | Q42 | 12285851.9 | 0 | 12285851.9 | 316597.3287 |  | 12602449.23 | 20113.7768 | 50528321.41 | 21270318.91 | 16655553.27 | 11658887.29 | 92.51%
Commercialisation | Q43 | 12602449.23 | 0 | 12602449.23 | 324755.9439 |  | 12927205.18 | 22225.1544 | 55832366.05 | 23503100.8 | 19402060.07 | 13581442.05 | 105.1%
Commercialisation | Q44 | 12927205.18 | 0 | 12927205.18 | 333124.6647 |  | 13260329.84 | 24547.6699 | 61666815.15 | 25959160.88 | 22447324.43 | 15713127.1 | 118.5%
Commercialisation | Q45 | 13260329.84 | 0 | 13260329.84 | 341709.0448 |  | 13602038.89 | 27102.4368 | 68084709.17 | 28660826.97 | 25821843.31 | 18075290.32 | 132.9%
Commercialisation | Q46 | 13602038.89 | 0 | 13602038.89 | 350514.6381 |  | 13952553.52 | 29912.6805 | 75144392.58 | 31632659.66 | 29559179.4 | 20691425.58 | 148.3%
Commercialisation | Q47 | 13952553.52 | 0 | 13952553.52 | 359547.1451 |  | 14312100.67 | 33003.9486 | 82910044.34 | 34901675.63 | 33696268.04 | 23587387.63 | 164.8%
Commercialisation | Q48 | 14312100.67 | 0 | 14312100.67 | 368812.4133 |  | 14680913.08 | 36404.3434 | 91452261.28 | 38497593.19 | 38273755 | 26791628.5 | 182.5%
Commercialisation | Q49 | 14680913.08 | 0 | 14680913.08 | 378316.4406 |  | 15059229.52 | 40144.7778 | 100848699.9 | 42453102.51 | 43336367.87 | 30335457.51 | 201.4%
Commercialisation | Q50 | 15059229.52 | 0 | 15059229.52 | 388065.3798 |  | 15447294.9 | 44259.2556 | 111184782.4 | 46804162.76 | 48933324.73 | 34253327.31 | 221.7%
Commercialisation | Q51 | 15447294.9 | 0 | 15447294.9 | 398065.5421 |  | 15845360.45 | 48785.1811 | 122554473.1 | 51590329.04 | 55118783.65 | 38583148.55 | 243.5%
Commercialisation | Q52 | 15845360.45 | 0 | 15845360.45 | 408323.4013 |  | 16253683.85 | 53763.6992 | 135061132.9 | 56855111.94 | 61952337.16 | 43366636.01 | 266.8%
Commercialisation | Q53 | 16253683.85 | 0 | 16253683.85 | 418845.598 |  | 16672529.44 | 59240.0692 | 148818458.7 | 62646373.14 | 69499556.16 | 48649689.31 | 291.8%
Commercialisation | Q54 | 16672529.44 | 0 | 16672529.44 | 429638.9441 |  | 17102168.39 | 65264.0761 | 163951517.1 | 69016760.45 | 77832588.28 | 54482811.79 | 318.6%

## Data for Financial Model
Task cost by Milestone | SUM of Task Cost |  | Total project Management Cost
1 | 903842.5 |  | 24890
2 | 2457000
3 | 2848806.25 |  | Innovation & Discovery Buffer
4 | 803250 |  | 1712348.26
5 | 124875
6 | 749250
Grand Total | 7887023.75
From - https://docs.google.com/spreadsheets/d/19gQoUNAgni2Q3cBqf_Fr74eUt1XlAO0jYqWVy-49ukw/edit?usp=sharing
Task Profile by Quarters | [10 empty] | Total
Quarter | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10
Task Cost | 1342593 | 1350000 | 600750 | 1485306 | 1417500 | 515250 | 385875 | 300375 | 263250 | 226125 | 7887024
Project Management by Quarters | [10 empty] | 0
Quarter | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | 0
Project Management Cost | 2489 | 2489 | 2489 | 2489 | 2489 | 2489 | 2489 | 2489 | 2489 | 2489 | 24890
0
Innovation & Discovery Buffer by Quarter
Quarter | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | 0
Innovation & Discovery Buffer* | 291489.7669 | 293097.8974 | 130428.5643 | 322474.1226 | 307752.7923 | 111865.6975 | 83777.149 | 65214.2822 | 57154.09 | 49093.8978 | 1712348.26
I would roll this up into Task Cost
Equipment Cost | 1636571.767 | 1645586.897 | 733667.5643 | 1810269.123 | 1727741.792 | 629604.6975 | 472141.149 | 368078.2822 | 322893.09 | 277707.8978 | 9624262.26
RP401 Development | 486.88 | [9 empty] | 234957.5
Learning Centre content about V2G, V2G in No Bill, V2G EVSE unit and install info, impacts on specific cars [warranty, safety, app, etc, etc] - Comms person - $1k/day - 10 days | 10350
Customer Journey design to include the the V2G product option - Service Designer - $2k/day - 5 days | 10350
Customer Journey implementation and testing to include the the V2G product option - Revenue Ops Engineer - $1k/day - 5 days | 4600
Customer App changes to include V2G storage - Senior Developer - $1.5k/day - 20 days | 18375
Fleet management system changes to incorporate V2G EVSE + Car Models - $1.5k/day - 15 days | 13475
Trialog ComboCS with OCPP + ISO 15118-20 | 34807.5
Starcharge Halo 7.4kW (single phase) | 35000
(maybe) Starcharge Halo 11kW (three phase) | 50000
(maybe) Lab Test Vehicle | 25000
Versinetic OCPP2.1 Licenses | 30000
AEMO PMS (FCAS) Registration Fee | 3000

## Task cost profile
[8 empty] | Milestone |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | Q1 | Q1 | Q1 | Q1 | Q1 | Q1 | Q1 | Q1 | Q1 | Q1 | Q1 | Q1 | Q1 | Q2 | Q2 | Q2 | Q2 | Q2 | Q2 | Q2 | Q2 | Q2 | Q2 | Q2 | Q2 | Q2 | Q3 | Q3 | Q3 | Q3 | Q3 | Q3 | Q3 | Q3 | Q3 | Q3 | Q3 | Q3 | Q3 | Q4 | Q4 | Q4 | Q4 | Q4 | Q4 | Q4 | Q4 | Q4 | Q4 | Q4 | Q4 | Q4 | Q5 | Q5 | Q5 | Q5 | Q5 | Q5 | Q5 | Q5 | Q5 | Q5 | Q5 | Q5 | Q5 | Q6 | Q6 | Q6 | Q6 | Q6 | Q6 | Q6 | Q6 | Q6 | Q6 | Q6 | Q6 | Q6 | Q7 | Q7 | Q7 | Q7 | Q7 | Q7 | Q7 | Q7 | Q7 | Q7 | Q7 | Q7 | Q7 | Q8 | Q8 | Q8 | Q8 | Q8 | Q8 | Q8 | Q8 | Q8 | Q8 | Q8 | Q8 | Q8 | Q9 | Q9 | Q9 | Q9 | Q9 | Q9 | Q9 | Q9 | Q9 | Q9 | Q9 | Q9 | Q9 | Q10 | Q10 | Q10 | Q10 | Q10 | Q10 | Q10 | Q10 | Q10 | Q10 | Q10 | Q10 | Q10
Milestone | Milestone Task | Task ID | Workstream | Task Name | Look up | Adjusted | Task Cost | Duration (Wks) | Week Cost | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52 | W53 | W54 | W55 | W56 | W57 | W58 | W59 | W60 | W61 | W62 | W63 | W64 | W65 | W66 | W67 | W68 | W69 | W70 | W71 | W72 | W73 | W74 | W75 | W76 | W77 | W78 | W79 | W80 | W81 | W82 | W83 | W84 | W85 | W86 | W87 | W88 | W89 | W90 | W91 | W92 | W93 | W94 | W95 | W96 | W97 | W98 | W99 | W100 | W101 | W102 | W103 | W104 | W105 | W106 | W107 | W108 | W109 | W110 | W111 | W112 | W113 | W114 | W115 | W116 | W117 | W118 | W119 | W120 | W121 | W122 | W123 | W124 | W125 | W126 | W127 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127
1 | 1 | 1.1 | Project Initiation | 1. Kickoff meeting and technical review between key technical partners |  | 3792.5 | 3792.5 | 1 | 3792.5 | [127 empty] | 3792.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: W1
1 | 2 | 1.2 | Project Initiation | Procure lab testing hardware & development kit. | 2300 |  | 2300 | 2 | 1150 | [127 empty] | 1150 | 1150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: W1 to W2
1 | 3 | 1.3 | Reposit Controller Hardware Enhancement | Design for three additional FCAS-compliant metering channels | [132 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: W1
1 | 4 | 1.4 | Reposit Controller Hardware Enhancement | Design for new SoC to support 6-channel FCAS metering & disjunctive optimisation | 270000 |  | 270000 | 1 | 270000 | [127 empty] | 0 | 270000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: W2
1 | 5 | 1.5 | Hardware Communication | Finalise ISO 15188-20 specification | 108000 |  | 108000 | 4 | 27000 | [127 empty] | 0 | 27000 | 27000 | 27000 | 27000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: W2 to W5
1 | 6 | 1.6 | Hardware Communication | Finalise OCPP2.1 specification | 81000 |  | 81000 | 3 | 27000 | [127 empty] | 0 | 27000 | 27000 | 27000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: W2 to W4
1 | 7 | 1.7 | Hardware Communication | Procure EVSE unit for lab testing | 20250 |  | 20250 | 1 | 20250 | [127 empty] | 20250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: W1
1 | 8 | 1.8 | Reposit Cloud Enhancement | Develop configuration tools & database structure for EVSE & Vehicle configuration | 135000 |  | 135000 | 5 | 27000 | [127 empty] | 27000 | 27000 | 27000 | 27000 | 27000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: W1 to W5
1 | 9 | 1.9 | Digital Trust Validation | Wireframe PKI specification agreed | 162000 |  | 162000 | 6 | 27000 | [127 empty] | 0 | 27000 | 27000 | 27000 | 27000 | 27000 | 27000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: W2 to W7
1 | 10 | 1.10 | Market Integration | Engage with DNSPs on connection approval requirements | 121500 |  | 121500 | 6 | 20250 | [127 empty] | 0 | 20250 | 20250 | 20250 | 20250 | 20250 | 20250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: W2 to W7
2 | 11 | 2.11 | Reposit Controller Software Enhancement | Develop bidirectional EVSE decision-making capabilities | 540000 |  | 540000 | 16 | 33750 | [127 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33750 | 33750 | 33750 | 33750 | 33750 | 33750 | 33750 | 33750 | 33750 | 33750 | 33750 | 33750 | 33750 | 33750 | 33750 | 33750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: W8 to W23
2 | 12 | 2.12 | Customer Product Development | Identify existing Reposit customers with potentially compatible vehicles | 40500 |  | 40500 | 2 | 20250 | [127 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20250 | 20250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: W9 to W10
2 | 13 | 2.13 | Hardware Communication | OCPP 2.1 server implemented on Reposit Controller | 540000 |  | 540000 | 16 | 33750 | [127 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33750 | 33750 | 33750 | 33750 | 33750 | 33750 | 33750 | 33750 | 33750 | 33750 | 33750 | 33750 | 33750 | 33750 | 33750 | 33750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: W12 to W27
2 | 14 | 2.14 | Hardware Communication | OCPP 2.1 client on EVSE | 472500 |  | 472500 | 14 | 33750 | [127 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33750 | 33750 | 33750 | 33750 | 33750 | 33750 | 33750 | 33750 | 33750 | 33750 | 33750 | 33750 | 33750 | 33750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: W12 to W25
2 | 15 | 2.15 | Hardware Communication | Test vehicle and EVSE ISO 15118-20 Communication | 202500 |  | 202500 | 6 | 33750 | [127 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33750 | 33750 | 33750 | 33750 | 33750 | 33750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: W13 to W18
2 | 16 | 2.16 | Reposit Controller Software Enhancement | Control Schema for EVSE Implemented | 472500 |  | 472500 | 14 | 33750 | [127 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33750 | 33750 | 33750 | 33750 | 33750 | 33750 | 33750 | 33750 | 33750 | 33750 | 33750 | 33750 | 33750 | 33750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: W28 to W41
2 | 17 | 2.17 | Hardware Communication | Test end-to-end telemetry from Reposit controller to BEV (notional - actual or mock BEV device) | 162000 |  | 162000 | 6 | 27000 | [127 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27000 | 27000 | 27000 | 27000 | 27000 | 27000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: W28 to W33
2 | 18 | 2.18 | Customer Product Development | Identify test vehicle (BYD provided, lent or acquired) | 27000 |  | 27000 | 2 | 13500 | [127 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13500 | 13500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: W8 to W9
3 | 19 | 3.19 | Hardware Communication | Test end-to-end power setpoint response from controller through to vehicle | 216000 |  | 216000 | 8 | 27000 | [127 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27000 | 27000 | 27000 | 27000 | 27000 | 27000 | 27000 | 27000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: W45 to W52
3 | 20 | 3.20 | Customer Product Development | Draft customer value proposition for initial No Bill product | 162000 |  | 162000 | 6 | 27000 | [127 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27000 | 27000 | 27000 | 27000 | 27000 | 27000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: W45 to W50
3 | 21 | 3.21 | Customer Product Development | Test notional product with prospective customers to validate uptake potential | 162000 |  | 162000 | 6 | 27000 | [127 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27000 | 27000 | 27000 | 27000 | 27000 | 27000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: W51 to W56
3 | 22 | 3.22 | Customer Product Development | Add key controls (i.e overrides) and data displays to Reposit app | 216000 |  | 216000 | 8 | 27000 | [127 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27000 | 27000 | 27000 | 27000 | 27000 | 27000 | 27000 | 27000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: W42 to W49
3 | 23 | 3.23 | Customer Product Development | In-App Customer Feedback engine | 306.25 |  | 306.25 | 2 | 153.125 | [127 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153.125 | 153.125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: W42 to W43
3 | 24 | 3.24 | Reposit Controller Hardware Enhancement | Finalise upgraded controller specifications and manufacture prototypes | 1350000 |  | 1350000 | 20 | 67500 | [127 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67500 | 67500 | 67500 | 67500 | 67500 | 67500 | 67500 | 67500 | 67500 | 67500 | 67500 | 67500 | 67500 | 67500 | 67500 | 67500 | 67500 | 67500 | 67500 | 67500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: W44 to W63
3 | 25 | 3.25 | Market Integration | Identify FCAS services which can be delivered via V2G | 81000 |  | 81000 | 4 | 20250 | [127 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20250 | 20250 | 20250 | 20250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: W53 to W56
3 | 26 | 3.26 | Reposit Controller Software Enhancement | Enhance frequency response control to enable V2G FCAS delivery | 135000 |  | 135000 | 10 | 13500 | [127 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13500 | 13500 | 13500 | 13500 | 13500 | 13500 | 13500 | 13500 | 13500 | 13500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: W57 to W66
3 | 27 | 3.27 | Reposit Controller Software Enhancement | Develop EV forecast engine (predict connectivity, energy needed for mobility) | 324000 |  | 324000 | 12 | 27000 | [127 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27000 | 27000 | 27000 | 27000 | 27000 | 27000 | 27000 | 27000 | 27000 | 27000 | 27000 | 27000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: W47 to W58
3 | 28 | 3.28 | Reposit Controller Software Enhancement | Implement new vehicle & EVSE metric collection and publication to cloud | 121500 |  | 121500 | 6 | 20250 | [127 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20250 | 20250 | 20250 | 20250 | 20250 | 20250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: W53 to W58
3 | 29 | 3.29 | Customer Product Development | End-to-end test from Reposit App, through to test vehicle | 81000 |  | 81000 | 4 | 20250 | [127 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20250 | 20250 | 20250 | 20250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: W59 to W62
4 | 30 | 4.30 | Customer Product Development | Employ & on-board customer concierge | 351000 |  | 351000 | 12 | 29250 | [127 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29250 | 29250 | 29250 | 29250 | 29250 | 29250 | 29250 | 29250 | 29250 | 29250 | 29250 | 29250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: W69 to W80
4 | 31 | 4.31 | Customer Product Development | T&C legal review | 13500 |  | 13500 | 2 | 6750 | [127 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6750 | 6750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: W69 to W70
4 | 32 | 4.32 | Customer Product Development | Finalise customer V2G product within project | 81000 |  | 81000 | 6 | 13500 | [127 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13500 | 13500 | 13500 | 13500 | 13500 | 13500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: W71 to W76
4 | 33 | 4.33 | Customer Product Development | Release updated Reposit App with EVSE+Vehicle support | 162000 |  | 162000 | 8 | 20250 | [127 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20250 | 20250 | 20250 | 20250 | 20250 | 20250 | 20250 | 20250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: W81 to W88
4 | 34 | 4.34 | Customer Product Development | Learning Centre expansion & Customer Support Training | 67500 |  | 67500 | 5 | 13500 | [127 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13500 | 13500 | 13500 | 13500 | 13500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: W77 to W81
4 | 35 | 4.35 | Product Deployment | Produce installation instructions, safety guidelines and other key material for installers | 40500 |  | 40500 | 4 | 10125 | [127 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10125 | 10125 | 10125 | 10125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: W71 to W74
4 | 36 | 4.36 | Product Deployment | Procure EVSE for customer installations | 13500 |  | 13500 | 2 | 6750 | [127 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6750 | 6750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: W77 to W78
4 | 37 | 4.37 | Customer Recruitment Marketing | Create and deploy marketing to identify customers for trial | 40500 |  | 40500 | 4 | 10125 | [127 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10125 | 10125 | 10125 | 10125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: W77 to W80
4 | 38 | 4.38 | Customer Recruitment Marketing | Recruit Gen1 customers | 20250 |  | 20250 | 3 | 6750 | [127 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6750 | 6750 | 6750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: W81 to W83
4 | 39 | 4.39 | Market Integration | Get DNSP approvals for Gen1 customer installations | 13500 |  | 13500 | 2 | 6750 | [127 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6750 | 6750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: W67 to W68
5 | 40 | 5.40 | Market Integration | Add Gen1 customers to RERT and/or MSL DUIDs | 13500 |  | 13500 | 2 | 6750 | [127 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6750 | 6750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: W89 to W90
5 | 41 | 5.41 | Product Deployment | Proceed with installation at rest of Gen1 customer sites | 54000 |  | 54000 | 4 | 13500 | [127 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13500 | 13500 | 13500 | 13500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: W89 to W92
5 | 42 | 5.42 | Digital Trust Validation | Internal review of PKI identification and security | 13500 |  | 13500 | 2 | 6750 | [127 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6750 | 6750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: W93 to W94
5 | 43 | 5.43 | Market Integration | Enable 5-minute spot price response on Gen1 sites | 30375 |  | 30375 | 3 | 10125 | [127 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10125 | 10125 | 10125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: W89 to W91
5 | 44 | 5.44 | Digital Trust Validation | Penetration testing by 3rd party | 13500 |  | 13500 | 2 | 6750 | [127 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6750 | 6750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: W95 to W96
6 | 45 | 6.45 | Customer Product Development | Develop & finalise experimental design for validating V2G No Bill product | 54000 |  | 54000 | 4 | 13500 | [127 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13500 | 13500 | 13500 | 13500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: W97 to W100
6 | 46 | 6.46 | Customer Product Development | Gather operational data from Gen1 sites over 6 months | 263250 |  | 263250 | 26 | 10125 | [127 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10125 | 10125 | 10125 | 10125 | 10125 | 10125 | 10125 | 10125 | 10125 | 10125 | 10125 | 10125 | 10125 | 10125 | 10125 | 10125 | 10125 | 10125 | 10125 | 10125 | 10125 | 10125 | 10125 | 10125 | 10125 | 10125 | 0 | 0 | 0 | 0 | 0 | bar: W97 to W122
6 | 47 | 6.47 | Data Collection and Reporting | Produce key data pack (raw data points, overviews of market participation) | 30375 |  | 30375 | 3 | 10125 | [127 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10125 | 10125 | 10125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: W97 to W99
6 | 48 | 6.48 | Data Collection and Reporting | Customer Experience Research/Feedback gathering | 54000 |  | 54000 | 4 | 13500 | [127 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13500 | 13500 | 13500 | 13500 | 0 | 0 | 0 | bar: W121 to W124
6 | 49 | 6.49 | Data Collection and Reporting | Reposit to reach determination on ongoing No Bill V2G offering | 13500 |  | 13500 | 2 | 6750 | [127 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6750 | 6750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: W97 to W98
6 | 50 | 6.50 | Data Collection and Reporting | Digital Trust Report, including pentesting results | 30375 |  | 30375 | 3 | 10125 | [127 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10125 | 10125 | 10125 | bar: W125 to W127
6 | 51 | 6.51 | Data Collection and Reporting | Produce recommendations report on lessons learnt and advice to industry | 303750 |  | 303750 | 30 | 10125 | [127 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10125 | 10125 | 10125 | 10125 | 10125 | 10125 | 10125 | 10125 | 10125 | 10125 | 10125 | 10125 | 10125 | 10125 | 10125 | 10125 | 10125 | 10125 | 10125 | 10125 | 10125 | 10125 | 10125 | 10125 | 10125 | 10125 | 10125 | 10125 | 10125 | 10125 | 0 | bar: W97 to W126
[137 empty] | 52192.5 | 399400 | 128250 | 128250 | 101250 | 47250 | 47250 | 47250 | 67500 | 54000 | 33750 | 101250 | 135000 | 135000 | 135000 | 135000 | 135000 | 135000 | 101250 | 101250 | 101250 | 101250 | 101250 | 67500 | 67500 | 33750 | 33750 | 60750 | 60750 | 60750 | 60750 | 60750 | 60750 | 33750 | 33750 | 33750 | 33750 | 33750 | 33750 | 33750 | 33750 | 27153.125 | 27153.125 | 94500 | 148500 | 148500 | 175500 | 175500 | 175500 | 148500 | 148500 | 148500 | 162000 | 162000 | 162000 | 162000 | 128250 | 128250 | 101250 | 101250 | 101250 | 101250 | 81000 | 13500 | 13500 | 13500 | 6750 | 6750 | 36000 | 36000 | 52875 | 52875 | 52875 | 52875 | 42750 | 42750 | 59625 | 59625 | 52875 | 52875 | 40500 | 27000 | 27000 | 20250 | 20250 | 20250 | 20250 | 20250 | 30375 | 30375 | 23625 | 13500 | 6750 | 6750 | 6750 | 6750 | 50625 | 50625 | 43875 | 33750 | 20250 | 20250 | 20250 | 20250 | 20250 | 20250 | 20250 | 20250 | 20250 | 20250 | 20250 | 20250 | 20250 | 20250 | 20250 | 20250 | 20250 | 20250 | 20250 | 20250 | 33750 | 33750 | 23625 | 23625 | 20250 | 20250 | 10125
[149 empty] | 1342592.5 | [12 empty] | 1350000 | [12 empty] | 600750 | [12 empty] | 1485306.25 | [12 empty] | 1417500 | [12 empty] | 515250 | [12 empty] | 385875 | [12 empty] | 300375 | [12 empty] | 263250 | [12 empty] | 226125

## Labour Rates
Role | Rate Per Day (RPD) | Rate Per Hour (RPH)
Project Manager | 1300 | 162.5
CEO | 2850 | 356.25
CFO | 1900 | 237.5
Senior Developer | 1225 | 153.125
Senior Energy Analyst | 1150 | 143.75
Financial controller | 1224 | 153
Engineering Developer | 1150 | 143.75
CTO | 1900 | 237.5
Project technical lead | 1300 | 162.5
External nil | 0 | 0
Reporting Lead | 1300 | 162.5
CX designer | 1150 | 143.75
Blended rate | 1350 | 168.75

## Workshop
WorkStream | Work Activity | Task Name | SUM of Total | Milestone | Outcome | Knowledge sharing
Market Development | Project Initiation | 1. Kickoff meeting and technical review between key technical partners | 16500 | 1 | Finalised project Plan | Lessons learnt on partner perspectives, expected challenges
| DERM Development - Controller | 2. Develop program dispatch and control technical specification | 70000 | 1 | Dispatch and Control specification | Dispatch and control specification
|  | 3. Develop MQTT implementation | 27500 | 1
|  | 4. Develop local OCPP 2.1 implementation | 82500 | 1 | Localised OCPP 2.1 | Description of OCPP2.1 and discussion on localisation recommendations
|  | 5. Develop program value computation strategy and technical requirements | 2340000 | 2 | (How much of this is IP - commercial in confidence) | Progress Report - Lessons learnt, challenges, issues, customer in
|  | 6. Develop and test DERM technical solution | 2340000 | 3 | (How much of this is IP - commercial in confidence) | Progress Report - Lesson learnt and test results
|  | 6. Operate and Maintain DERM technical solution | 0
|  | 7. Release to production environment | 0
| Customer-related works | 8. Develop conceptual customer offering in lieu of BESS at site | 12500 | 1 | Proposed Customer Offer | Customer insights, proposed offer,
|  | 9. Undertake detailed economic study of value potentials (dependent on 1/3 of field trials being completed for existing customers) | 50000 | 1 | High level revenue forefast prediction Market analysis | High level value stacking (not optomised)
|  | 10. Finalise V2G-only customer offering | 12500
|  | 11. Prepare stage 2 trial customer agreement materials | 12500
|  | 12. Legal advice | 40000
|  | 13. Content development about V2G, V2G in No Bill, V2G EVSE unit and install info, impacts on specific cars (warranty, safety, app, etc, etc) | 10000
|  | 14. Customer Journey design to include the the V2G product option | 10000
|  | 15. Customer Journey implementation and testing to include the the V2G product option | 5000
|  | 16. Customer App changes to include V2G storage | 80000
|  | 17. Fleet management system changes to incorporate V2G EVSE + Car Models | 60000
|  | 18. Go to market, acquire 10 V2G-only customers | 45000
|  | 19. Conduct research on protocol learnings for interoperable DERMs in V2G contexts | 60000
|  | 20. Prepare and release report to OCA | 17875
|  | 21. Prepare and release report to CharIN | 17875
| Customer-related works Total |  | 433250
| Knowledge Sharing | 22. Prepare and release report to Standards Australia | 35750
|  | 23. Finalise report on MQTT vs OCPP control | 30000
|  | 24. Finalise report on value sharing | 69000
| Knowledge Sharing Total |  | 134750
| EVSE | 25. Delivery and installation of EVSEs | 0
|  | 26. Develop V2G installation SWMS | 2500
|  | 27. Order and delivery of V2G EVSEs | 6000
|  | 28. Installation of first 20 EVSEs to existing customers | 158400
|  | 29. Installation of last 10 EVSEs to new customers | 79200
|  | 30. V2G VPP trials | 0
|  | 31. EV OEM 1 | 0
|  | 32. VPP live on EV OEM 1 vehicles - existing customers | 65760
|  | 33. VPP live on EV OEM 1 vehicles - new customers | 65760
|  | 34. EV OEM 2 | 0
|  | 35. VPP live on EV OEM 2 vehicles - existing customers | 65760
|  | 36. VPP live on EV OEM 2 vehicles - new customers | 65760
|  | 37. EV OEM 3 | 0
|  | 38. VPP live on EV OEM 3 vehicles - existing customers | 65760
|  | 39. VPP live on EV OEM 3 vehicles - new customers | 65760
|  | 40. EV OEM 4 | 0
|  | 41. VPP live on EV OEM 4 vehicles - existing customers | 65760
|  | 42. VPP live on EV OEM 4 vehicles - new customers | 65760
|  | 43. EV OEM 5 | 0
|  | 44. VPP live on EV OEM 5 vehicles - existing customers | 65760
|  | 45. VPP live on EV OEM 5 vehicles - new customers | 65760
|  | 46. V2G VPP trial closeout | 0
|  | 47. EV OEM 1 cohort | 0
|  | 48. Return phase 1 OEM 1 vehicles to OEM | 1500
|  | 49. Return phase 2 OEM 1 vehicles to OEM | 1500
|  | 50. Transfer phase 1 OEM 1 customers to production code, remove any trial infrastructure | 1500
|  | 51. Transfer phase 2 OEM 1 customers to production code, remove any trial infrastructure | 1500
|  | 52. EV OEM 2 cohort | 0
|  | 53. Return phase 1 OEM 2 vehicles to OEM | 1500
|  | 54. Return phase 2 OEM 2 vehicles to OEM | 1500
|  | 55. Transfer phase 1 OEM 2 customers to production code, remove any trial infrastructure | 1500
|  | 56. Transfer phase 2 OEM 2 customers to production code, remove any trial infrastructure | 1500
|  | 57. EV OEM 3 cohort | 0
|  | 58. Return phase 1 OEM 3 vehicles to OEM | 1500
|  | 59. Return phase 2 OEM 3 vehicles to OEM | 1500
|  | 60. Transfer phase 1 OEM 3 customers to production code, remove any trial infrastructure | 1500
|  | 61. Transfer phase 2 OEM 3 customers to production code, remove any trial infrastructure | 1500
|  | 62. EV OEM 4 cohort | 0
|  | 63. Return phase 1 OEM 4 vehicles to OEM | 1500
|  | 64. Return phase 2 OEM 4 vehicles to OEM | 1500
|  | 65. Transfer phase 1 OEM 4 customers to production code, remove any trial infrastructure | 1500
|  | 66. Transfer phase 2 OEM 4 customers to production code, remove any trial infrastructure | 1500
|  | 67. EV OEM 5 cohort | 0
|  | 68. Return phase 1 OEM 5 vehicles to OEM | 1500
|  | 69. Return phase 2 OEM 5 vehicles to OEM | 1500
|  | 70. Transfer phase 1 OEM 5 customers to production code, remove any trial infrastructure | 1500
|  | 71. Transfer phase 2 OEM 5 customers to production code, remove any trial infrastructure | 1500
|  | 72. Customer trial portion complete | 0
|  | 73. Upgraded gateway metrology for multi-FCAS | 0
|  | 74. Specification and planning | 36000
|  | 75. Design and development | 120000
|  | 76. Prototyping and validation | 60000
|  | 77. Certification and pilot production | 120000
|  | 78. Production ramp up | 100000
| EVSE Total |  | 1369700
Market Development Total |  |  | 6814200
Digital Trust |  | 1. Development of V2G PKI performance targets against Australian and international cybersecurity landscape (internal report for ENA) | 91500 | 1
|  | 2. Consultation on V2G PKI performance targets | 97500
|  | 3. Final reporting on V2G PKI performance targets | 6250
|  | 4. Development of private PKI / test environment processes for ISO 15118-2 | 250
|  | 5. Development of private PKI / test environment processes for ISO 15118-20 | 250
|  | 6. Development of processes to provision and use Hubject APAC PKI in ISO 15118-2 secured charging | 3125
|  | 7. Development of processes to provision and use Hubject APAC PKI in ISO 15118-20 secured charging | 3125
|  | 8. OEM 1 Hubject integration | 17500
|  | 9. OEM 2 Hubject integration | 17500
|  | 10. OEM 3 Hubject integration | 17500
|  | 11. OEM 4 Hubject integration | 17500
|  | 12. OEM 5 Hubject integration | 17500
|  | 13. Development of report detailing PKI processes for secured charging in Australia under ISO 15118-2 and ISO 15118-20 | 159000
|  | 14. Consultation on report detailing PKI processes for secured charging in Australia under ISO 15118-2 and ISO 15118-20 | 75750
|  | 15. Finalisation of report detailing PKI processes for secured charging in Australia under ISO 15118-2 and ISO 15118-20 | 16250
|  | 16. Publishing of report detailing PKI processes for secured charging in Australia under ISO 15118-2 and ISO 15118-20 | 0
|  | 17. Study of proliferation, scalability and implementation requirements of ISO 15118 PKI ecosystems in Australia | 148500
|  | 18. Review of work, key systems and components inherent throughout the project compiled in the context of a study of knowledge, standards gaps and value transferability study for AC V2G | 148500
Digital Trust Total |  |  | 837500
Project Management | Corporate Services | 3. Accounting (blended salary rate) | 157200
|  | 4. Authorship | 117900
|  | 5. Escalation and signoff | 35370
| Corporate Services Total |  | 310470
| PMO | 1. Project Manager | 3537000
| PMO Total |  | 3537000
| Steering Committee | 2. Steering committee particpation | 229905
| Steering Committee Total |  | 229905
Project Management Total |  |  | 4077375
Grand Total |  |  | 11729075

## Gantt
Task ID | Workstream | Task Name | Dependencies | Duration (Wks) | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52 | W53 | W54 | W55 | W56 | W57 | W58 | W59 | W60 | W61
1.1 | Project Initiation | 1. Kickoff meeting and technical review between key technical partners |  | 1 | W1: 1.1
1.2 | Project Initiation | 1. Kickoff meeting and technical review between key technical partners |  | 1 | W1: 1.2
1.3 | Project Initiation | 1. Kickoff meeting and technical review between key technical partners |  | 1 | W1: 1.3
1.4 | Project Initiation | 1. Kickoff meeting and technical review between key technical partners |  | 2 | W1: 1.4
1.5 | Project Initiation | Procure lab testing hardware & development kit. |  | 2 | W1: 1.5
1.6 | Reposit Controller Hardware Enhancement | Design for three additional FCAS-compliant metering channels |  | 1 | W1: 1.6
1.1 | Hardware Communication | Procure EVSE unit for lab testing |  | 1 | W1: 1.1
1.11 | Reposit Cloud Enhancement | Develop configuration tools & database structure for EVSE & Vehicle configuration |  | 5 | W1: 1.11
2.14 | Reposit Controller Software Enhancement | Develop bidirectional EVSE decision-making capabilities |  | 16 | W1: 2.14
2.21 | Customer Product Development | Identify test vehicle (BYD provided, lent or acquired) | 2.2 | 2 | W1: 2.21
3.26 | Customer Product Development | Add key controls (i.e overrides) and data displays to Reposit app |  | 8 | W1: 3.26
3.27 | Customer Product Development | In-App Customer Feedback engine |  | 2 | W1: 3.27
5.45 | Market Integration | Add Gen1 customers to RERT and/or MSL DUIDs | 5.46 | 2 | W1: 5.45
5.46 | Product Deployment | Proceed with installation at rest of Gen1 customer sites | 5.45 | 4 | W1: 5.46
5.48 | Market Integration | Enable 5-minute spot price response on Gen1 sites | 5.46 | 3 | W1: 5.48
6.46 | Customer Product Development | Develop & finalise experimental design for validating V2G No Bill product | 5.45 | 4 | W1: 6.46
6.47 | Customer Product Development | Gather operational data from Gen1 sites over 6 months | 5.46 | 26 | W1: 6.47
6.48 | Data Collection and Reporting | Produce key data pack (raw data points, overviews of market participation) | 6.47 | 3 | W1: 6.48
6.5 | Data Collection and Reporting | Reposit to reach determination on ongoing No Bill V2G offering | 6.47 | 2 | W1: 6.5
6.52 | Data Collection and Reporting | Produce recommendations report on lessons learnt and advice to industry | 6.47 | 30 | W1: 6.52
1.7 | Reposit Controller Hardware Enhancement | Design for new SoC to support 6-channel FCAS metering & disjunctive optimisation | 1.6 | 1 | W2: 1.7
1.8 | Hardware Communication | Finalise ISO 15188-20 specification | 1.1 | 4 | W2: 1.8
1.9 | Hardware Communication | Finalise OCPP2.1 specification | 1.1 | 3 | W2: 1.9
1.12 | Digital Trust Validation | Wireframe PKI specification agreed | 1.1 | 6 | W2: 1.12
1.13 | Market Integration | Engage with DNSPs on connection approval requirements | 1.1 | 6 | W2: 1.13
2.15 | Customer Product Development | Identify existing Reposit customers with potentially compatible vehicles | 1.1 | 2 | W2: 2.15
3.22 | Vehicle Offering Finalisation | Vehicle OEM provides test vehicle(s) and/or firmware version for testing | 2.21 | 1 | W3: 3.22
3.28 | Reposit Controller Hardware Enhancement | Finalise upgraded controller specifications and manufacture prototypes | 1.7 | 20 | W3: 3.28
3.23 | Hardware Communication | Test end-to-end power setpoint response from controller through to vehicle | 3.22 | 8 | W4: 3.23
3.24 | Customer Product Development | Draft customer value proposition for initial No Bill product | 2.15 | 6 | W4: 3.24
4.34 | Vehicle Offering Finalisation | Vehicle OEM produces warranty terms or waivers specifically covering vehicles used within the project | 3.22 | 3 | W4: 4.34
2.16 | Hardware Communication | OCPP 2.1 server implemented on Reposit Controller | 1.9 | 16 | W5: 2.16
2.17 | Hardware Communication | OCPP 2.1 client on EVSE | 1.9 | 14 | W5: 2.17
2.18 | Hardware Communication | Test vehicle and EVSE ISO 15118-20 Communication | 1.8 | 6 | W6: 2.18
3.31 | Reposit Controller Software Enhancement | Develop EV forecast engine (predict connectivity, energy needed for mobility) | 1.11 | 12 | W6: 3.31
4.44 | Market Integration | Get DNSP approvals for Gen1 customer installations | 1.13 | 2 | W8: 4.44
3.25 | Customer Product Development | Test notional product with prospective customers to validate uptake potential | 3.24 | 6 | W10: 3.25
4.35 | Customer Product Development | Employ & on-board customer concierge | 3.24 | 52 | W10: 4.35
4.36 | Customer Product Development | T&C legal review | 3.24 | 2 | W10: 4.36
3.29 | Market Integration | Identify FCAS services which can be delivered via V2G | 3.23 | 4 | W12: 3.29
3.32 | Reposit Controller Software Enhancement | Implement new vehicle & EVSE metric collection and publication to cloud | 3.23 | 6 | W12: 3.32
4.37 | Customer Product Development | Finalise customer V2G product within project | 4.36 | 6 | W12: 4.37
4.4 | Product Deployment | Produce installation instructions, safety guidelines and other key material for installers | 3.23 | 4 | W12: 4.4
3.3 | Reposit Controller Software Enhancement | Enhance frequency response control to enable V2G FCAS delivery | 3.29 | 10 | W16: 3.3
3.33 | Customer Product Development | End-to-end test from Reposit App, through to test vehicle | 3.32 | 4 | W18: 3.33
4.39 | Customer Product Development | Learning Centre expansion & Customer Support Training | 4.37 | 5 | W18: 4.39
4.41 | Product Deployment | Procure EVSE for customer installations | 4.37 | 2 | W18: 4.41
4.42 | Customer Recruitment Marketing | Create and deploy marketing to identify customers for trial | 4.37 | 4 | W18: 4.42
2.19 | Reposit Controller Software Enhancement | Control Schema for EVSE Implemented | 2.16 | 14 | W21: 2.19
2.2 | Hardware Communication | Test end-to-end telemetry from Reposit controller to BEV (notional - actual or mock BEV device) | 2.16, 2.17, 1.10 | 6 | W21: 2.2
4.38 | Customer Product Development | Release updated Reposit App with EVSE+Vehicle support | 3.33 | 8 | W22: 4.38
4.43 | Customer Recruitment Marketing | Recruit Gen1 customers | 4.42 | 3 | W22: 4.43
5.47 | Digital Trust Validation | Internal review of PKI identification and security | 4.43 | 2 | W25: 5.47
6.49 | Data Collection and Reporting | Customer Experience Research/Feedback gathering | 4.43 | 4 | W25: 6.49
5.49 | Digital Trust Validation | Penetration testing by 3rd party | 5.47 | 2 | W27: 5.49
6.51 | Data Collection and Reporting | Digital Trust Report, including pentesting results | 5.49 | 3 | W29: 6.51