## Draft Budget and Schedule (hidden)
WorkStream | Work Activity | Task Name | Duration | Start | Finish | Expense Type | Entity | Role | Cash/in kind | Budget | Fixed Cost Item | Days | Daily Rate | Salary (built up) | FTE | Total days | Total | In-kind % | Cash | In-kind | Comment 1 | Comment 2 | Comment 3
Market Development | Project Initiation | Kickoff meeting and technical review between key technical partners | 5 days | Mon 02/03/26 | Fri 06/03/26 | Salary | RedEarth | CTO | Cash |  |  | 5 |  | 301368 | 0.2 | 1 | 1205 |  | 1205 | 0 | 3314841.05 | 3603300
Market Development | Project Initiation |  |  |  |  | Salary | RedEarth | Technical Lead | Cash |  |  | 5 | 2500 |  | 0.2 | 1 | 2500 |  | 2500 | 0
Market Development | Project Initiation |  |  |  |  | Salary | Reposit Power | Consultant | Both |  |  | 5 | 2500 |  | 0.2 | 1 | 2500 |  | 2500 | 0 |  | Reposit cash | Reposit in-kind
Market Development | Project Initiation |  |  |  |  | Salary | Ambibox | Consultant | Both |  |  | 5 | 2500 |  | 0.2 | 1 | 2500 |  | 2500 | 0 |  | $2,790,600.00 | $3,311,000.00
Market Development | Project Initiation |  |  |  |  | Advisors/Consultants | Other | Engineering Developer (Intemp) | Cash |  |  | 5 | 2000 |  | 0.2 | 1 | 2000 |  | 2000 | 0
Market Development | Server-side DERM development |  | 100 days | Mon 09/03/26 | Fri 24/07/26
Market Development | Server-side DERM development | Develop program dispatch and control technical specification | 20 days | Mon 09/03/26 | Fri 03/04/26 | Salary | Reposit Power | Developer, senior | Both |  |  | 20 | 4000 |  | 0.5 | 10 | 40000 | 50% | 20000 | 20000
Market Development | Server-side DERM development |  |  |  |  | Salary | Reposit Power | Developer | Both |  |  | 20 | 3000 |  | 0.5 | 10 | 30000 | 50% | 15000 | 15000
Market Development | Server-side DERM development | Develop MQTT implementation | 5 days | Mon 06/04/26 | Fri 10/04/26 | Salary | Reposit Power | Developer | Cash |  |  | 5 | 3000 |  | 1 | 5 | 15000 |  | 15000 | 0
Market Development | Server-side DERM development |  |  |  |  | Salary | Ambibox | Consultant | Cash |  |  | 5 | 2500 |  | 1 | 5 | 12500 |  | 12500 | 0
Market Development | Server-side DERM development | Develop local OCPP 2.1 implementation | 15 days | Mon 13/04/26 | Fri 01/05/26 | Salary | Reposit Power | Developer | Cash |  |  | 15 | 3000 |  | 1 | 15 | 45000 |  | 45000 | 0
Market Development | Server-side DERM development |  |  |  |  | Salary | Ambibox | Consultant | Cash |  |  | 15 | 2500 |  | 1 | 15 | 37500 |  | 37500 | 0
Market Development | Server-side DERM development | Develop program value computation strategy and technical requirements | 520 | Mon 09/03/26 | Fri 03/04/26 | Salary | Reposit Power | Developer, senior | Both |  |  | 520 | 4000 |  | 0.5 | 260 | 1040000 | 80% | 208000 | 832000
Market Development | Server-side DERM development |  |  | -183 |  | Salary | Reposit Power | Developer | Both |  |  | 520 | 3000 |  | 0.5 | 260 | 780000 | 80% | 156000 | 624000
Market Development | Server-side DERM development |  |  |  |  | Salary | Reposit Power | Developer, junior | Both |  |  | 520 | 2000 |  | 0.5 | 260 | 520000 | 80% | 104000 | 416000
Market Development | Server-side DERM development | Develop and test DERM technical solution | 520 | Mon 04/05/26 | Fri 24/07/26 | Salary | Reposit Power | Developer, senior | Both |  |  | 520 | 4000 |  | 0.5 | 260 | 1040000 | 60% | 416000 | 624000
Market Development | Server-side DERM development |  |  |  |  | Salary | Reposit Power | Developer | Both |  |  | 520 | 3000 |  | 0.5 | 260 | 780000 | 60% | 312000 | 468000
Market Development | Server-side DERM development |  |  |  |  | Salary | Reposit Power | Developer, junior | Both |  |  | 520 | 2000 |  | 0.5 | 260 | 520000 | 60% | 208000 | 312000
Market Development | Server-side DERM development | Release to production environment | 0 days | Fri 24/07/26 | Fri 24/07/26
Market Development | Customer-related works |  | 1345.84 days | Mon 09/03/26 | Tue 05/05/31
Market Development | Customer-related works | Develop conceptual customer offering in lieu of BESS at site | 5 days | Mon 27/07/26 | Fri 31/07/26 | Salary | Reposit Power | Product developer | Cash |  |  | 10 | 2500 |  | 1 | 10 | 25000 |  | 25000 | 0
Market Development | Customer-related works | Undertake detailed economic study of value potentials (dependent on 1/3 of field trials being completed for existing customers) | 20 days | Wed 23/08/28 | Wed 20/09/28 | Salary | Reposit Power | Product developer | Cash |  |  | 20 | 2500 |  | 1 | 20 | 50000 |  | 50000 | 0
Market Development | Customer-related works | Finalise V2G-only customer offering | 5 days | Wed 20/09/28 | Wed 27/09/28 | Salary | Reposit Power | Product developer | Cash |  |  | 5 | 2500 |  | 1 | 5 | 12500 |  | 12500 | 0
Market Development | Customer-related works | Prepare stage 2 trial customer agreement materials | 5 days | Wed 27/09/28 | Wed 4/10/28 | Salary | Reposit Power | Product developer | Cash |  |  | 5 | 2500 |  | 1 | 5 | 12500 |  | 12500 | 0
Market Development | Customer-related works | Legal advice | 10 |  |  | Advisors/Consultants | Other | External lawyer | Cash |  |  | 10 | 4000 |  | 1 | 10 | 40000 |  | 40000 | 0
Market Development | Customer-related works | Learning Centre content about V2G, V2G in No Bill, V2G EVSE unit and install info, impacts on specific cars (warranty, safety, app, etc, etc) | 10 |  |  | Salary | Reposit Power | Comms staff | Cash |  |  | 10 | 1000 |  | 1 | 10 | 10000 |  | 10000 | 0
Market Development | Customer-related works | Customer Journey design to include the the V2G product option | 5 |  |  | Salary | Reposit Power | Service designer | Cash |  |  | 5 | 2000 |  | 1 | 5 | 10000 |  | 10000 | 0
Market Development | Customer-related works | Customer Journey implementation and testing to include the the V2G product option | 5 |  |  | Salary | Reposit Power | Revenue ops engineer | Cash |  |  | 5 | 1000 |  | 1 | 5 | 5000 |  | 5000 | 0
Market Development | Customer-related works | Customer App changes to include V2G storage | 20 |  |  | Salary | Reposit Power | Developer, senior | Cash |  |  | 20 | 4000 |  | 1 | 20 | 80000 |  | 80000 | 0
Market Development | Customer-related works | Fleet management system changes to incorporate V2G EVSE + Car Models | 15 |  |  | Salary | Reposit Power | Developer, senior | Cash |  |  | 15 | 4000 |  | 1 | 15 | 60000 |  | 60000 | 0
Market Development | Customer-related works | Go to market, acquire 10 V2G-only customers | 30 days | Wed 4/10/28 | Wed 15/11/28 | Salary | Reposit Power | Business development | Cash |  |  | 30 | 1500 |  | 1 | 30 | 45000 |  | 45000 | 0
Market Development | Customer-related works | Conduct research on protocol learnings for interoperable DERMs in V2G contexts | 40 | Wed 20/09/28 | Wed 1/11/28 | Salary | RACEfor2030 | Research team | Both |  |  | 40 | 1500 |  | 1 | 40 | 60000 | 50% | 30000 | 30000
Market Development | Customer-related works | Prepare and release report to OCA | 5 days | Wed 1/11/28 | Wed 8/11/28 | Salary | RedEarth | Technical Lead | Cash |  |  | 5 | 2500 |  | 1 | 5 | 12500 |  | 12500 | 0
Market Development | Customer-related works |  |  |  |  | Salary | Ambibox | Consultant | Cash |  |  | 5 | 2500 |  | 0.25 | 1.25 | 3125 |  | 3125 | 0
Market Development | Customer-related works |  |  |  |  | Salary | RedEarth | CTO | Cash |  |  | 5 |  | 301368 | 0.1 | 0.5 | 603 |  | 603 | 0
Market Development | Customer-related works | Prepare and release report to CharIN | 5 days | Wed 8/11/28 | Wed 15/11/28 | Salary | RedEarth | Technical Lead | Cash |  |  | 5 | 2500 |  | 1 | 5 | 12500 |  | 12500 | 0
Market Development | Customer-related works |  |  |  |  | Salary | Ambibox | Consultant | Cash |  |  | 5 | 2500 |  | 0.25 | 1.25 | 3125 |  | 3125 | 0
Market Development | Customer-related works |  |  |  |  | Salary | RedEarth | CTO | Cash |  |  | 5 |  | 301368 | 0.1 | 0.5 | 603 |  | 603 | 0
Market Development | Reporting | Prepare and release report to Standards Australia | 10 days | Wed 15/11/28 | Wed 29/11/28 | Salary | RedEarth | Technical Lead | Cash |  |  | 10 | 2500 |  | 1 | 10 | 25000 |  | 25000 | 0
Market Development | Reporting |  |  |  |  | Salary | Ambibox | Consultant | Cash |  |  | 10 | 2500 |  | 0.25 | 2.5 | 6250 |  | 6250 | 0
Market Development | Reporting |  |  |  |  | Salary | RedEarth | CTO | Cash |  |  | 5 |  | 301368 | 0.1 | 0.5 | 603 |  | 603 | 0
Market Development | Reporting | Finalise report on MQTT vs OCPP control | 20 days | Wed 1/11/28 | Wed 29/11/28 | Salary | RACEfor2030 | Research team | Both |  |  | 30 | 1500 |  | 1 | 30 | 45000 | 50% | 22500 | 22500
Market Development | Reporting | Finalise report on value sharing | 50 days | Tue 24/02/31 | Tue 05/05/31 | Salary | Reposit Power | Product developer | Cash |  |  | 50 | 2500 |  | 0.5 | 25 | 62500 |  | 62500 | 0
Market Development | Reporting |  |  |  |  | Salary | RedEarth | Technical Lead | Cash |  |  | 50 | 2500 |  | 0.5 | 25 | 62500 |  | 62500 | 0
Market Development | Reporting |  |  |  |  | Salary | Ambibox | Consultant | Cash |  |  | 50 | 2500 |  | 0.2 | 10 | 25000 |  | 25000 | 0
Market Development | Reporting |  |  |  |  | Salary | RedEarth | CTO | Cash |  |  | 50 |  | 301368 | 0.1 | 5 | 6027 |  | 6027 | 0
Market Development | Workstream complete |  | 0 days | Tue 05/05/31 | Tue 05/05/31
Market Development | EVSE | Delivery and installation of EVSEs | 1298.84 days | Mon 09/03/26 | Fri 27/02/31
Market Development | EVSE | Develop V2G installation SWMS | 2 days | Mon 09/03/26 | Tue 10/03/26 | Salary | Reposit Power | Product developer | Cash |  |  | 2 | 2500 |  | 0.5 | 1 | 2500 |  | 2500 | 0
Market Development | EVSE | Order and delivery of V2G EVSEs | 60 days | Wed 11/03/26 | Tue 02/06/26 | Shipping & Logistics | Other | Logistics | Cash |  | 4500 | 60 | 1500 |  | 0.05 | 3 | 4500 |  | 4500 | 0
Market Development | EVSE |  |  |  |  | Shipping & Logistics | Reposit Power | Warehousing | Cash |  | 1500 | 60 | 50 |  | 0.5 | 30 | 1500 |  | 1500 | 0
Market Development | EVSE | Installation of first 20 EVSEs to existing customers | 90 days | Wed 03/06/26 | Tue 6/10/26 | Equipment | Reposit Power | Install cost EVSE | Cash |  |  | 90 | 8000 |  | 0.22 | 20 | 160000 |  | 160000 | 0
Market Development | EVSE | Installation of last 10 EVSEs to new customers | 45 days | Wed 15/11/28 | Wed 17/01/29 | Equipment | Reposit Power | Install cost EVSE | Cash |  |  | 45 | 8000 |  | 0.22 | 10 | 80000 |  | 80000 | 0
Market Development | EVSE | V2G VPP trials | 918.84 days | Wed 18/08/27 | Tue 24/02/31
Market Development | EVSE | EV OEM 1 | 833.84 days | Wed 15/12/27 | Tue 24/02/31
Market Development | EVSE | VPP live on EV OEM 1 vehicles - existing customers | 548 days | Wed 15/12/27 | Sat 18/01/30 | Salary | Reposit Power | Customer service | Both |  |  | 548 | 1200 |  | 0.1 | 54.8 | 65760 |  | 65760 | 0
Market Development | EVSE | VPP live on EV OEM 1 vehicles - new customers | 548 days | Wed 17/01/29 | Tue 24/02/31 | Salary | Reposit Power | Customer service | Both |  |  | 548 | 1200 |  | 0.1 | 54.8 | 65760 |  | 65760 | 0
Market Development | EVSE | EV OEM 2 | 918.84 days | Wed 18/08/27 | Tue 24/02/31
Market Development | EVSE | VPP live on EV OEM 2 vehicles - existing customers | 548 days | Wed 15/12/27 | Sat 18/01/30 | Salary | Reposit Power | Customer service | Both |  |  | 548 | 1200 |  | 0.1 | 54.8 | 65760 |  | 65760 | 0
Market Development | EVSE | VPP live on EV OEM 2 vehicles - new customers | 548 days | Wed 17/01/29 | Tue 24/02/31 | Salary | Reposit Power | Customer service | Both |  |  | 548 | 1200 |  | 0.1 | 54.8 | 65760 |  | 65760 | 0
Market Development | EVSE | EV OEM 3 | 918.84 days | Wed 18/08/27 | Tue 24/02/31
Market Development | EVSE | VPP live on EV OEM 3 vehicles - existing customers | 548 days | Wed 15/12/27 | Sat 18/01/30 | Salary | Reposit Power | Customer service | Both |  |  | 548 | 1200 |  | 0.1 | 54.8 | 65760 |  | 65760 | 0
Market Development | EVSE | VPP live on EV OEM 3 vehicles - new customers | 548 days | Wed 17/01/29 | Tue 24/02/31 | Salary | Reposit Power | Customer service | Both |  |  | 548 | 1200 |  | 0.1 | 54.8 | 65760 |  | 65760 | 0
Market Development | EVSE | EV OEM 4 | 918.84 days | Wed 18/08/27 | Tue 24/02/31
Market Development | EVSE | VPP live on EV OEM 4 vehicles - existing customers | 548 days | Wed 15/12/27 | Sat 18/01/30 | Salary | Reposit Power | Customer service | Both |  |  | 548 | 1200 |  | 0.1 | 54.8 | 65760 |  | 65760 | 0
Market Development | EVSE | VPP live on EV OEM 4 vehicles - new customers | 548 days | Wed 17/01/29 | Tue 24/02/31 | Salary | Reposit Power | Customer service | Both |  |  | 548 | 1200 |  | 0.1 | 54.8 | 65760 |  | 65760 | 0
Market Development | EVSE | EV OEM 5 | 918.84 days | Wed 18/08/27 | Tue 24/02/31
Market Development | EVSE | VPP live on EV OEM 5 vehicles - existing customers | 548 days | Wed 15/12/27 | Sat 18/01/30 | Salary | Reposit Power | Customer service | Both |  |  | 548 | 1200 |  | 0.1 | 54.8 | 65760 |  | 65760 | 0
Market Development | EVSE | VPP live on EV OEM 5 vehicles - new customers | 548 days | Wed 17/01/29 | Tue 24/02/31 | Salary | Reposit Power | Customer service | Both |  |  | 548 | 1200 |  | 0.1 | 54.8 | 65760 |  | 65760 | 0
Market Development | EVSE | V2G VPP trial closeout | 373.84 days | Mon 24/09/29 | Fri 27/02/31
Market Development | EVSE | EV OEM 1 cohort | 288.84 days | Tue 21/01/30 | Fri 27/02/31
Market Development | EVSE | Return phase 1 OEM 1 vehicles to OEM | 3 days | Tue 21/01/30 | Thu 23/01/30 | Shipping & Logistics | OEM 1 | Transport | Cash |  | 1500 | 3 | 500 |  | 1 | 3 | 1500 |  | 1500 | 0
Market Development | EVSE | Return phase 2 OEM 1 vehicles to OEM | 3 days | Tue 24/02/31 | Fri 27/02/31 | Shipping & Logistics | OEM 1 | Transport | Cash |  | 1500 | 3 | 500 |  | 1 | 3 | 1500 |  | 1500 | 0
Market Development | EVSE | Transfer phase 1 OEM 1 customers to production code, remove any trial infrastructure | 1 day | Tue 21/01/30 | Tue 21/01/30 | Salary | Reposit Power | Developer | Cash |  |  | 1 | 3000 |  | 0.5 | 0.5 | 1500 |  | 1500 | 0
Market Development | EVSE | Transfer phase 2 OEM 1 customers to production code, remove any trial infrastructure | 1 day | Tue 24/02/31 | Wed 25/02/31 | Salary | Reposit Power | Developer | Cash |  |  | 1 | 3000 |  | 0.5 | 0.5 | 1500 |  | 1500 | 0
Market Development | EVSE | EV OEM 2 cohort | 373.84 days | Mon 24/09/29 | Thu 27/02/31
Market Development | EVSE | Return phase 1 OEM 2 vehicles to OEM | 3 days | Mon 24/09/29 | Wed 26/09/29 | Shipping & Logistics | OEM 2 | Transport | Cash |  | 1500 | 3 | 500 |  | 1 | 3 | 1500 |  | 1500 | 0
Market Development | EVSE | Return phase 2 OEM 2 vehicles to OEM | 3 days | Mon 24/02/31 | Thu 27/02/31 | Shipping & Logistics | OEM 2 | Transport | Cash |  | 1500 | 3 | 500 |  | 1 | 3 | 1500 |  | 1500 | 0
Market Development | EVSE | Transfer phase 1 OEM 2 customers to production code, remove any trial infrastructure | 1 day | Mon 24/09/29 | Mon 24/09/29 | Salary | Reposit Power | Developer | Cash |  |  | 1 | 3000 |  | 0.5 | 0.5 | 1500 |  | 1500 | 0
Market Development | EVSE | Transfer phase 2 OEM 2 customers to production code, remove any trial infrastructure | 1 day | Mon 24/02/31 | Tue 25/02/31 | Salary | Reposit Power | Developer | Cash |  |  | 1 | 3000 |  | 0.5 | 0.5 | 1500 |  | 1500 | 0
Market Development | EVSE | EV OEM 3 cohort | 373.84 days | Mon 24/09/29 | Thu 27/02/31
Market Development | EVSE | Return phase 1 OEM 3 vehicles to OEM | 3 days | Mon 24/09/29 | Wed 26/09/29 | Shipping & Logistics | OEM 3 | Transport | Cash |  | 1500 | 3 | 500 |  | 1 | 3 | 1500 |  | 1500 | 0
Market Development | EVSE | Return phase 2 OEM 3 vehicles to OEM | 3 days | Mon 24/02/31 | Thu 27/02/31 | Shipping & Logistics | OEM 3 | Transport | Cash |  | 1500 | 3 | 500 |  | 1 | 3 | 1500 |  | 1500 | 0
Market Development | EVSE | Transfer phase 1 OEM 3 customers to production code, remove any trial infrastructure | 1 day | Mon 24/09/29 | Mon 24/09/29 | Salary | Reposit Power | Developer | Cash |  |  | 1 | 3000 |  | 0.5 | 0.5 | 1500 |  | 1500 | 0
Market Development | EVSE | Transfer phase 2 OEM 3 customers to production code, remove any trial infrastructure | 1 day | Mon 24/02/31 | Tue 25/02/31 | Salary | Reposit Power | Developer | Cash |  |  | 1 | 3000 |  | 0.5 | 0.5 | 1500 |  | 1500 | 0
Market Development | EVSE | EV OEM 4 cohort | 373.84 days | Mon 24/09/29 | Thu 27/02/31
Market Development | EVSE | Return phase 1 OEM 4 vehicles to OEM | 3 days | Mon 24/09/29 | Wed 26/09/29 | Shipping & Logistics | OEM 4 | Transport | Cash |  | 1500 | 3 | 500 |  | 1 | 3 | 1500 |  | 1500 | 0
Market Development | EVSE | Return phase 2 OEM 4 vehicles to OEM | 3 days | Mon 24/02/31 | Thu 27/02/31 | Shipping & Logistics | OEM 4 | Transport | Cash |  | 1500 | 3 | 500 |  | 1 | 3 | 1500 |  | 1500 | 0
Market Development | EVSE | Transfer phase 1 OEM 4 customers to production code, remove any trial infrastructure | 1 day | Mon 24/09/29 | Mon 24/09/29 | Salary | Reposit Power | Developer | Cash |  |  | 1 | 3000 |  | 0.5 | 0.5 | 1500 |  | 1500 | 0
Market Development | EVSE | Transfer phase 2 OEM 4 customers to production code, remove any trial infrastructure | 1 day | Mon 24/02/31 | Tue 25/02/31 | Salary | Reposit Power | Developer | Cash |  |  | 1 | 3000 |  | 0.5 | 0.5 | 1500 |  | 1500 | 0
Market Development | EVSE | EV OEM 5 cohort | 373.84 days | Mon 24/09/29 | Thu 27/02/31
Market Development | EVSE | Return phase 1 OEM 5 vehicles to OEM | 3 days | Mon 24/09/29 | Wed 26/09/29 | Shipping & Logistics | OEM 5 | Transport | Cash |  | 1500 | 3 | 500 |  | 1 | 3 | 1500 |  | 1500 | 0
Market Development | EVSE | Return phase 2 OEM 5 vehicles to OEM | 3 days | Mon 24/02/31 | Thu 27/02/31 | Shipping & Logistics | OEM 5 | Transport | Cash |  | 1500 | 3 | 500 |  | 1 | 3 | 1500 |  | 1500 | 0
Market Development | EVSE | Transfer phase 1 OEM 5 customers to production code, remove any trial infrastructure | 1 day | Mon 24/09/29 | Mon 24/09/29 | Salary | Reposit Power | Developer | Cash |  |  | 1 | 3000 |  | 0.5 | 0.5 | 1500 |  | 1500 | 0
Market Development | EVSE | Transfer phase 2 OEM 5 customers to production code, remove any trial infrastructure | 1 day | Mon 24/02/31 | Tue 25/02/31 | Salary | Reposit Power | Developer | Cash |  |  | 1 | 3000 |  | 0.5 | 0.5 | 1500 |  | 1500 | 0
Market Development | EVSE | Customer trial portion complete | 0 days | Thu 27/02/31 | Thu 27/02/31
Market Development | EVSE | Upgraded gateway metrology for multi-FCAS | 1323.84 days | Mon 06/04/26 | Fri 01/05/31
Market Development | EVSE | Specification and planning | 18 | Mon 06/04/26 | Wed 08/04/26 | Advisors/Consultants | Other | Engineering Developer (Intemp) | Both |  |  | 18 | 2000 |  | 1 | 18 | 36000 | 40% | 21600 | 14400 |  | Insert componets for FCAS metering on dedvice
Market Development | EVSE | Design and development | 60 |  |  | Advisors/Consultants | Other | Engineering Developer (Intemp) | Both |  |  | 60 | 2000 |  | 1 | 60 | 120000 | 40% | 72000 | 48000 |  | Insert componets for FCAS metering on dedvice
Market Development | EVSE | Prototyping and validation | 30 | Fri 27/02/31 | Fri 13/03/31 | Advisors/Consultants | Other | Engineering Developer (Intemp) | Both |  |  | 30 | 2000 |  | 1 | 30 | 60000 | 50% | 30000 | 30000 |  | Insert componets for FCAS metering on dedvice
Market Development | EVSE | Certification and pilot production | 60 | Fri 13/03/31 | Fri 20/03/31 | Advisors/Consultants | Other | Engineering Developer (Intemp) | Both |  |  | 60 | 2000 |  | 1 | 60 | 120000 | 67% | 39600 | 80400 |  | Insert componets for FCAS metering on dedvice
Market Development | EVSE | Production ramp up | 50 | Fri 20/03/31 | Fri 01/05/31 | Advisors/Consultants | Other | Engineering Developer (Intemp) | Both |  |  | 50 | 2000 |  | 1 | 50 | 100000 | 67% | 33000 | 67000 |  | Insert componets for FCAS metering on dedvice
Digital Trust | WS5 | Development of V2G PKI performance targets against Australian and international cybersecurity landscape (internal report for ENA) | 30 days | Mon 02/03/26 | Fri 10/04/26 | Salary | RedEarth | Technical Lead | Cash |  |  | 30
Digital Trust | WS5 |  |  |  |  | Salary | ENA | EV WG | In-kind |  |  | 30 | 2500 |  | 0.5 | 15 | 37500 |  | 0 | 37500
Digital Trust | WS5 |  |  |  |  | Advisors/Consultants | Other | Hubject Consultant | Cash |  |  | 30 | 5500 |  | 0.1 | 3 | 16500 |  | 16500 | 0
Digital Trust | WS5 | Consultation on V2G PKI performance targets | 30 days | Mon 13/04/26 | Fri 22/05/26 | Salary | RedEarth | Technical Lead | Cash |  |  | 30 | 2500 |  | 0.5 | 15 | 37500 |  | 37500 | 0
Digital Trust | WS5 |  |  |  |  | Salary | ENA | EV WG | In-kind |  |  | 30 | 4000 |  | 0.5 | 15 | 60000 |  | 0 | 60000
Digital Trust | WS5 | Final reporting on V2G PKI performance targets | 5 days | Mon 25/05/26 | Fri 29/05/26 | Salary | RedEarth | Technical Lead | Cash |  |  | 30 | 2500 |  | 0.5 | 15 | 37500 |  | 37500 | 0
Digital Trust | WS5 | Development of private PKI / test environment processes for ISO 15118-2 | 1 | Mon 01/06/26 | Fri 12/06/26 | Salary | Ambibox | Consultant | Cash |  |  | 10 | 2500 |  | 0.1 | 1 | 2500 |  | 2500 | 0
Digital Trust | WS5 | Development of private PKI / test environment processes for ISO 15118-20 | 1 | Mon 15/06/26 | Fri 03/07/26 | Salary | Ambibox | Consultant | Cash |  |  | 15 | 2500 |  | 0.1 | 1.5 | 3750 |  | 3750 | 0
Digital Trust | WS5 | Development of processes to provision and use Hubject APAC PKI in ISO 15118-2 secured charging | 1 | Mon 06/07/26 | Fri 10/07/26 | Salary | Ambibox | Consultant | Cash |  |  | 1 | 2500 |  | 1 | 1 | 2500 |  | 2500 | 0
Digital Trust | WS5 |  |  |  |  | Salary | RedEarth | Technical Lead | Cash |  |  | 1 | 2500 |  | 0.25 | 0.25 | 625 |  | 625 | 0
Digital Trust | WS5 | Development of processes to provision and use Hubject APAC PKI in ISO 15118-20 secured charging | 1 | Mon 13/07/26 | Fri 24/07/26 | Salary | Ambibox | Consultant | Cash |  |  | 1 | 2500 |  | 1 | 1 | 2500 |  | 2500 | 0
Digital Trust | WS5 |  |  |  |  | Salary | RedEarth | Technical Lead | Cash |  |  | 1 | 2500 |  | 0.25 | 0.25 | 625 |  | 625 | 0
Digital Trust | WS5 | OEM 1 Hubject integration | 5 |  |  | Salary | Ambibox | Consultant | Cash |  |  | 5 | 2500 |  | 1 | 5 | 12500 |  | 12500 | 0
Digital Trust | WS5 |  |  |  |  | Other | Ambibox | Lab use | Cash |  |  | 5 | 1000 |  | 1 | 5 | 5000 |  | 5000 | 0
Digital Trust | WS5 | OEM 2 Hubject integration | 5 |  |  | Salary | Ambibox | Consultant | Cash |  |  | 5 | 2500 |  | 1 | 5 | 12500 |  | 12500 | 0
Digital Trust | WS5 |  |  |  |  | Other | Ambibox | Lab use | Cash |  |  | 5 | 1000 |  | 1 | 5 | 5000 |  | 5000 | 0
Digital Trust | WS5 | OEM 3 Hubject integration | 5 |  |  | Salary | Ambibox | Consultant | Cash |  |  | 5 | 2500 |  | 1 | 5 | 12500 |  | 12500 | 0
Digital Trust | WS5 |  |  |  |  | Other | Ambibox | Lab use | Cash |  |  | 5 | 1000 |  | 1 | 5 | 5000 |  | 5000 | 0
Digital Trust | WS5 | OEM 4 Hubject integration | 5 |  |  | Salary | Ambibox | Consultant | Cash |  |  | 5 | 2500 |  | 1 | 5 | 12500 |  | 12500 | 0
Digital Trust | WS5 |  |  |  |  | Other | Ambibox | Lab use | Cash |  |  | 5 | 1000 |  | 1 | 5 | 5000 |  | 5000 | 0
Digital Trust | WS5 | OEM 5 Hubject integration | 5 |  |  | Salary | Ambibox | Consultant | Cash |  |  | 5 | 2500 |  | 1 | 5 | 12500 |  | 12500 | 0
Digital Trust | WS5 |  |  |  |  | Other | Ambibox | Lab use | Cash |  |  | 5 | 1000 |  | 1 | 5 | 5000 |  | 5000 | 0
Digital Trust | WS5 | Development of report detailing PKI processes for secured charging in Australia under ISO 15118-2 and ISO 15118-20 | 30 days | Mon 27/07/26 | Fri 04/09/26 | Salary | ENA | EV WG | In-kind |  |  | 30 | 4000 |  | 0.2 | 6 | 24000 |  | 0 | 24000
Digital Trust | WS5 |  |  |  |  | Salary | Ambibox | CTO | Cash |  |  | 30 | 2500 |  | 0.25 | 7.5 | 18750 |  | 18750 | 0
Digital Trust | WS5 |  |  |  |  | Advisors/Consultants | Other | Hubject Consultant | Cash |  |  | 30 | 5500 |  | 0.25 | 7.5 | 41250 |  | 41250 | 0
Digital Trust | WS5 |  |  |  |  | Salary | RedEarth | Technical Lead | Cash |  |  | 30 | 2500 |  | 1 | 30 | 75000 |  | 75000 | 0
Digital Trust | WS5 | Consultation on report detailing PKI processes for secured charging in Australia under ISO 15118-2 and ISO 15118-20 | 30 days | Mon 07/09/26 | Fri 16/10/26 | Salary | ENA | EV WG | In-kind |  |  | 30 | 4000 |  | 0.2 | 6 | 24000 |  | 0 | 24000
Digital Trust | WS5 |  |  |  |  | Salary | RedEarth | Technical Lead | Cash |  |  | 30 | 2500 |  | 0.25 | 7.5 | 18750 |  | 18750 | 0
Digital Trust | WS5 |  |  |  |  | Advisors/Consultants | Other | Hubject Consultant | Cash |  |  | 30 | 5500 |  | 0.2 | 6 | 33000 |  | 33000 | 0
Digital Trust | WS5 | Finalisation of report detailing PKI processes for secured charging in Australia under ISO 15118-2 and ISO 15118-20 | 5 days | Mon 19/10/26 | Fri 23/10/26 | Salary | ENA | EV WG | Cash |  |  | 5 | 4000 |  | 0.5 | 2.5 | 10000 |  | 10000 | 0
Digital Trust | WS5 |  |  |  |  | Salary | RedEarth | Technical Lead | Cash |  |  | 5 | 2500 |  | 0.5 | 2.5 | 6250 |  | 6250 | 0
Digital Trust | WS5 | Publishing of report detailing PKI processes for secured charging in Australia under ISO 15118-2 and ISO 15118-20 | 0 days | Fri 23/10/26 | Fri 23/10/26 |  |  |  | Cash
Digital Trust | WS5 | Study of proliferation, scalability and implementation requirements of ISO 15118 PKI ecosystems in Australia | 132 | Mon 07/09/26 | Fri 05/03/27 | Salary | RACEfor2030 | Research - senior academic | Cash |  |  | 132 | 800 |  | 1 | 132 | 105600 |  | 105600 | 0
Digital Trust | WS5 |  |  |  |  | Salary | RedEarth | Technical Lead | Cash |  |  | 132 | 2500 |  | 0.05 | 6.6 | 16500 |  | 16500 | 0
Digital Trust | WS5 |  |  |  |  | Salary | ENA | EV WG | In-kind |  |  | 132 | 4000 |  | 0.05 | 6.6 | 26400 |  | 0 | 26400
Digital Trust | WS5 | Review of work, key systems and components inherent throughout the project compiled in the context of a study of knowledge, standards gaps and value transferability study for AC V2G | 132 | Tue 31/03/31 | Tue 29/09/31 | Salary | RACEfor2030 | Research - senior academic | Cash |  |  | 132 | 800 |  | 1 | 132 | 105600 |  | 105600 | 0
Digital Trust | WS5 |  |  |  |  | Salary | Ambibox | Consultant |  |  |  | 132 | 2500 |  | 0.05 | 6.6 | 16500 |  | 0 | 0
Digital Trust | WS5 |  |  |  |  | Salary | ENA | EV WG | In-kind |  |  | 132 | 4000 |  | 0.05 | 6.6 | 26400 |  | 0 | 26400
Project Management | PMO | Program Management | Project | Tue 29/09/31 | Wed 30/09/31
Project Management | PMO | Steering committee particpation | 786 | Tue 29/09/31 | Wed 30/09/31 | Project Management | RedEarth | CEO | Cash |  |  | 786 |  | 431505 | 0.02 | 15.72 | 27133 |  | 27133 | 0
Project Management | PMO | Steering committee particpation | 786 | Tue 29/09/31 | Wed 30/09/31 | Project Management | RedEarth | CFO | Cash |  |  | 36 |  | 376711 | 0.5 | 18 | 27123 |  | 27123 | 0
Project Management | PMO | Steering committee participation | 786 | Tue 29/09/31 | Wed 30/09/31 | Project Management | RedEarth | CTO | Cash |  |  | 36 |  | 301368 | 0.5 | 18 | 21699 |  | 21699 | 0
Project Management | PMO | Steering committee participation | 786 | Tue 29/09/31 | Wed 30/09/31 | Project Management | Ambibox | CTO | Cash |  |  | 36 | 2500 |  | 0.5 | 18 | 45000 |  | 45000 | 0
Project Management | PMO | Project Manager | 786 | Tue 29/09/31 | Wed 30/09/31 | Project Management | RedEarth | Project Manager | Cash |  |  | 786 |  | 180000 | 1 | 786 | 565920 |  | 565920 | 0
Project Management | PMO | Accounting (blended salary rate) | 786 | Tue 29/09/31 | Wed 30/09/31 | Project Management | RedEarth | Finance | Cash |  |  | 786 |  | 150000 | 0.25 | 196.5 | 117900 |  | 117900 | 0
Project Management | PMO | Regular reporting | Project | Tue 29/09/31 | Wed 30/09/31
Project Management | PMO | Authorship | 786 | Tue 29/09/31 | Wed 30/09/31 | Project Management | RedEarth | Reporting Lead | Cash |  |  | 786 |  | 150000 | 0.2 | 157.2 | 94320 |  | 94320 | 0
Project Management | PMO | Escalation and signoff | 786 | Tue 29/09/31 | Wed 30/09/31 | Project Management | RedEarth | CEO | Cash |  |  | 786 |  | 431505 | 0.05 | 39.3 | 67833 |  | 67833 | 0

## Revised Budget and Schedule
Milestone ( sequential view) | Task ID | Workstream | Task Name | Commencement Dependencies | Description of work to be done | Start | Finish | Working weeks in period | Hours per week avg | Project hours / units | Entity | Role | Blended rate / hour | Cost | Type | Total Project Costs | Contingency | All in
Continuous |  | Project Management | 1. Project Manager |  | Coordinate internal and external teams. Track milestones. Report on progress. Manage stakeholders. Report | 2026-06-01 | 2028-06-01 | 104.8 | 2 | 209.6 | Advisors/Consultants | Project manager | 162.5 | 34060 | Time | 8366741.3 | 20% | 10040089.56
Continuous |  | Project Management | 1. Project Manager |  | Coordinate internal and external teams. Track milestones. Report on progress. Manage stakeholders. Report | 2026-06-01 | 2028-06-01 | 104.8 | 2 | 209.6 | Advisors/Consultants | Project technical lead | 162.5 | 34060 | Time
Continuous |  | Project Management | 2. Steering committee participation |  | Provide technical oversight and direction | 2026-06-01 | 2028-06-01 | 104.8 | 1 | 104.8 | Reposit Power | CEO | 356.25 | 37335 | Time
Continuous |  | Project Management | 2. Steering committee participation |  | Provide technical oversight and direction | 2026-06-01 | 2028-06-01 | 104.8 | 1 | 104.8 | Reposit Power | CFO | 237.5 | 24890 | Time
Continuous |  | Project Management | 2. Steering committee participation |  | Provide technical oversight and direction | 2026-06-01 | 2028-06-01 | 104.8 | 1 | 104.8 | Reposit Power | CTO | 237.5 | 24890 | Time
Continuous |  | Project Management | 2. Steering committee participation |  | Provide technical oversight and direction | 2026-06-01 | 2028-06-01 | 104.8 | 1 | 104.8 | Ambibox | CTO | 237.5 | 24890 | Time
Continuous |  | Project Management | 2. Steering committee participation |  | Provide technical oversight and direction | 2026-06-01 | 2028-06-01 | 104.8 | 0 | 0 | Race2030 | External nil | 0 | 0 | Time
Continuous |  | Project Management | 2. Steering committee participation |  | Provide technical oversight and direction | 2026-06-01 | 2028-06-01 | 104.8 | 0 | 0 | ENA | External nil | 0 | 0 | Time
Continuous |  | Project Management | 2. Steering committee participation |  | Provide technical oversight and direction | 2026-06-01 | 2028-06-01 | 104.8 | 0 | 0 | ARENA Observer | External nil | 0 | 0 | Time
Continuous |  | Project Management | 3. Accounting (blended salary rate) |  | Reconcile and track time sheets and budgets | 2026-06-01 | 2028-06-01 | 104.8 | 2 | 209.6 | Reposit Power | Financial controller | 153 | 32068.8 | Time
Continuous |  | Project Management | 4. Authorship |  | As and when required | 2026-06-01 | 2028-06-01 | 104.8 | 0.25 | 26.2 | Reposit Power | Reporting Lead | 162.5 | 4257.5 | Time
Continuous |  | Project Management | 5. Escalation and signoff |  | As and when required | 2026-06-01 | 2028-06-01 | 104.8 | 0.25 | 26.2 | Reposit Power | CEO | 356.25 | 9333.75 | Time
1 | 1.1 | Project Initiation | 1. Kickoff meeting and technical review between key technical partners |  | Define scope of current stage | 2026-06-01 | 2026-06-06 | 1 | 4 | 4 | Reposit Power | CEO | 356.25 | 1425 | Time
1 | 1.2 | Project Initiation | 1. Kickoff meeting and technical review between key technical partners |  | Define scope of current stage | 2026-06-01 | 2026-06-06 | 1 | 4 | 4 | Reposit Power | CTO | 237.5 | 950 | Time
1 | 1.3 | Project Initiation | 1. Kickoff meeting and technical review between key technical partners |  | Define scope of current stage | 2026-06-01 | 2026-06-06 | 1 | 4 | 4 | Reposit Power | Senior Developer | 153.125 | 612.5 | Time
1 | 1.4 | Project Initiation | 1. Kickoff meeting and technical review between key technical partners |  | Define scope of current stage | 2026-06-01 | 2026-06-09 | 1.4 | 4 | 5.6 | Reposit Power | Engineering Developer | 143.75 | 805 | Time
1 | 1.5 | Project Initiation | Procure lab testing hardware & development kit. |  | Purchase and set up equipment for testing communication implementations (likely Trialog ComboS). Outcome - project initiated, standards implementation confidence, confident you can progress - testing validity of progressing at that point | 2026-06-13 | 2026-06-27 | 2 | 8 | 16 | Reposit Power | Engineering Developer | 143.75 | 2300 | Time
1 | 1.6 | Reposit Controller Hardware Enhancement | Design for three additional FCAS-compliant metering channels |  | Create verification of vehicle response - high speed to the bidirectional charging signal | tba | tba | [5 empty] | 0 | 750000 | Direct cost
1 | 1.7 | Reposit Controller Hardware Enhancement | Design for new SoC to support 6-channel FCAS metering & disjunctive optimisation | 1.6 | Supports the enhanced metering, and facilitate the upgrade to OCPP2.1 | tba | tba | [5 empty] | 0 | 0
1 | 1.8 | Hardware Communication | Finalise ISO 15188-20 specification | 1.1 | Agreeing with BEV that the standard will be implemented in a consistent way. - Progress report and lessons learnt on standards readiness, implementation and bi-directional charging feasibility |  |  | 4 | 160 | 640 | Reposit Power | Blended rate | 168.75 | 108000 | Time
1 | 1.9 | Hardware Communication | Finalise OCPP2.1 specification | 1.1 | Reposit and EVSE (bi directional charger) agreement that OCPP2.1 will be implemented consistently |  |  | 3 | 160 | 480 | Reposit Power | Blended rate | 168.75 | 81000 | Time
1 | 1.10 | Hardware Communication | Procure EVSE unit for lab testing |  | Reposit to procure the target EVSE for installation in their lab environment |  |  | 1 | 120 | 120 | Reposit Power | Blended rate | 168.75 | 20250 | Time
1 | 1.11 | Reposit Cloud Enhancement | Develop configuration tools & database structure for EVSE & Vehicle configuration |  | Build system to identify, store, and record the BEV |  |  | 5 | 160 | 800 | Reposit Power | Blended rate | 168.75 | 135000 | Time
1 | 1.12 | Digital Trust Validation | Wireframe PKI specification agreed | 1.1 | Agreement on the implementation of security certificate for BEV OEM (car supplier)and EVSE (car charger) |  |  | 6 | 160 | 960 | Reposit Power | Blended rate | 168.75 | 162000 | Time
1 | 1.13 | Market Integration | Engage with DNSPs on connection approval requirements | 1.1 | Confirm DNSP bidirectional charger application process and requirements |  |  | 6 | 120 | 720 | Reposit Power | Blended rate | 168.75 | 121500 | Time
| . | [11 empty] | 0 | 0 | Time
2 | 2.14 | Reposit Controller Software Enhancement | Develop bidirectional EVSE decision-making capabilities |  | Develop bidirectional charging capability within the Reposit controller |  |  | 16 | 200 | 3200 | Reposit Power | Blended rate | 168.75 | 540000 | Time
2 | 2.15 | Customer Product Development | Identify existing Reposit customers with potentially compatible vehicles | 1.1 | Potential customer identification within reposit existing customers - requires that they have eligible cars |  |  | 2 | 120 | 240 | Reposit Power | Blended rate | 168.75 | 40500 | Time
2 | 2.16 | Hardware Communication | OCPP 2.1 server implemented on Reposit Controller | 1.9 | Standard implemented on Reposit controller |  |  | 16 | 200 | 3200 | Reposit Power | Blended rate | 168.75 | 540000 | Time
2 | 2.17 | Hardware Communication | OCPP 2.1 client on EVSE | 1.9 | Standard implemented on Car charger. (- can a reposit controller send charge and discharge signals, and receive state of charge in test environment) |  |  | 14 | 200 | 2800 | Reposit Power | Blended rate | 168.75 | 472500 | Time
2 | 2.18 | Hardware Communication | Test vehicle and EVSE ISO 15118-20 Communication | 1.8 | Test standard implemented successfully. ("- Progress report, lessons learnt and success of hardware upgrade implementations ANd necessary updates on initially agreed specifications") |  |  | 6 | 200 | 1200 | Reposit Power | Blended rate | 168.75 | 202500 | Time
2 | 2.19 | Reposit Controller Software Enhancement | Control Schema for EVSE Implemented | 2.16 | Reposit controller capable of sending car charger charge or discharge signals, and receive state of charge from BEV |  |  | 14 | 200 | 2800 | Reposit Power | Blended rate | 168.75 | 472500 | Time
2 | 2.20 | Hardware Communication | Test end-to-end telemetry from Reposit controller to BEV (notional - actual or mock BEV device) | 2.16, 2.17, 1.10 | Communications test for hardware |  |  | 6 | 160 | 960 | Reposit Power | Blended rate | 168.75 | 162000 | Time
2 | 2.21 | Customer Product Development | Identify test vehicle (BYD provided, lent or acquired) | 2.2 | Determine how Reposit will access an appropriate BEV to complete demonstration test in Milestone 3 |  |  | 2 | 80 | 160 | Reposit Power | Blended rate | 168.75 | 27000 | Time
| . | [8 empty] | 0 | Reposit Power | Blended rate | 168.75 | 0 | Time
3 | 3.22 | Vehicle Offering Finalisation | Vehicle OEM provides test vehicle(s) and/or firmware version for testing | 2.21 | Acquire vehicle for testing. - using test vehicle to ensure that the system is fully operational, standards are implemented and functional, and reposit system and app are ready for BEV customers |  |  | 1 | 8 | 8 | Reposit Power | Blended rate | 168.75 | 1350 | Time
3 | 3.23 | Hardware Communication | Test end-to-end power setpoint response from controller through to vehicle | 3.22 | Test of system response time, which will inform what grid and system services can be delivered. - Preparing the technology for the demonstration project |  |  | 8 | 160 | 1280 | Reposit Power | Blended rate | 168.75 | 216000 | Time
3 | 3.24 | Customer Product Development | Draft customer value proposition for initial No Bill product | 2.15 | Develop product for the customer offering |  |  | 6 | 160 | 960 | Reposit Power | Blended rate | 168.75 | 162000 | Time
3 | 3.25 | Customer Product Development | Test notional product with prospective customers to validate uptake potential | 3.24 | Socialise product offering with customers and determine attractiveness |  |  | 6 | 160 | 960 | Reposit Power | Blended rate | 168.75 | 162000 | Time
3 | 3.26 | Customer Product Development | Add key controls (i.e overrides) and data displays to Reposit app |  | Enhance existing Reposit app to include key BEV features, i.e override and BEV data displays |  |  | 8 | 160 | 1280 | Reposit Power | Blended rate | 168.75 | 216000 | Time
3 | 3.27 | Customer Product Development | In-App Customer Feedback engine |  |  |  |  | 2 | 1 | 2 | Reposit Power | Senior Developer | 153.125 | 306.25 | Time
3 | 3.28 | Reposit Controller Hardware Enhancement | Finalise upgraded controller specifications and manufacture prototypes | 1.7 |  |  |  | 20 | 200 | 4000 | LAURENCE | Blended rate | 168.75 | 675000 | Time
3 | 3.29 | Market Integration | Identify FCAS services which can be delivered via V2G | 3.23 |  |  |  | 4 | 120 | 480 | Reposit Power | Blended rate | 168.75 | 81000 | Time
3 | 3.30 | Reposit Controller Software Enhancement | Enhance frequency response control to enable V2G FCAS delivery | 3.29 | Upgrade reposit controller to enable FCAS response from BEV |  |  | 10 | 80 | 800 | Reposit Power | Blended rate | 168.75 | 135000 | Time
3 | 3.31 | Reposit Controller Software Enhancement | Develop EV forecast engine (predict connectivity, energy needed for mobility) | 1.11 | Build a forecast engine to be able to predict BEV availability and state of charge |  |  | 12 | 160 | 1920 | Reposit Power | Blended rate | 168.75 | 324000 | Time
3 | 3.32 | Reposit Controller Software Enhancement | Implement new vehicle & EVSE metric collection and publication to cloud | 3.23 | Develop ability to collect information from EVSE (Car charger) and BEV (car) and store on Reposit's cloud |  |  | 6 | 120 | 720 | Reposit Power | Blended rate | 168.75 | 121500 | Time
3 | 3.33 | Customer Product Development | End-to-end test from Reposit App, through to test vehicle | 3.32 | Full test of end to end system functionality on test vehicle |  |  | 4 | 120 | 480 | Reposit Power | Blended rate | 168.75 | 81000 | Time
| . | [8 empty] | 0 | Reposit Power | Blended rate | 168.75 | 0 | Time
4 | 4.34 | Vehicle Offering Finalisation | Vehicle OEM produces warranty terms or waivers specifically covering vehicles used within the project | 3.22 | - Acquiring 5 customers (Gen 1), get warranty waivers, develop and execute customer terms and conditions, de |  |  | 3 | 60 | 180 | Reposit Power | Blended rate | 168.75 | 30375 | Time
4 | 4.35 | Customer Product Development | Employ & on-board customer concierge | 3.24 |  |  |  | 52 | 40 | 2080 | Reposit Power | Blended rate | 168.75 | 351000 | Time
4 | 4.36 | Customer Product Development | T&C legal review | 3.24 |  |  |  | 2 | 40 | 80 | Reposit Power | Blended rate | 168.75 | 13500 | Time
4 | 4.37 | Customer Product Development | Finalise customer V2G product within project | 4.36 |  |  |  | 6 | 80 | 480 | Reposit Power | Blended rate | 168.75 | 81000 | Time
4 | 4.38 | Customer Product Development | Release updated Reposit App with EVSE+Vehicle support | 3.33 | Update Reposit App to enable BEV integration |  |  | 8 | 120 | 960 | Reposit Power | Blended rate | 168.75 | 162000 | Time
4 | 4.39 | Customer Product Development | Learning Centre expansion & Customer Support Training | 4.37 | Develop and publish educational articles for Deposits learning center, and support guides for customer support team |  |  | 5 | 80 | 400 | Reposit Power | Blended rate | 168.75 | 67500 | Time
4 | 4.40 | Product Deployment | Produce installation instructions, safety guidelines and other key material for installers | 3.23 | Develop how-to guides for installers to ensure compliance and full functionality |  |  | 4 | 60 | 240 | Reposit Power | Blended rate | 168.75 | 40500 | Time
4 | 4.41 | Product Deployment | Procure EVSE for customer installations | 4.37 | Purchase EVSE units for customer installs |  |  | 2 | 40 | 80 | Reposit Power | Blended rate | 168.75 | 13500 | Time
4 | 4.42 | Customer Recruitment Marketing | Create and deploy marketing to identify customers for trial | 4.37 | Begin customer acquisition marketing |  |  | 4 | 60 | 240 | Reposit Power | Blended rate | 168.75 | 40500 | Time
4 | 4.43 | Customer Recruitment Marketing | Recruit Gen1 customers | 4.42 | Identify minimum of 5 customers to participate in the demonstration project (Gen1) |  |  | 3 | 40 | 120 | Reposit Power | Blended rate | 168.75 | 20250 | Time
4 | 4.44 | Market Integration | Get DNSP approvals for Gen1 customer installations | 1.13 | Gain DNSP connection approval for bidirectional chargers |  |  | 2 | 40 | 80 | Reposit Power | Blended rate | 168.75 | 13500 | Time
| . | [8 empty] | 0 | Reposit Power | Blended rate | 168.75 | 0 | Time
5 | 5.45 | Product Deployment | Identify first 1 or 2 flagship install sites, and install with oversight and review | 4.44 | Complete installations at initial Gen 1 sites (1 or 2), with heavy oversight to ensure installation is compliance and correct. Initialise and finalise preparation for demonstration trial |  |  | 5 | 80 | 400 | Reposit Power | Blended rate | 168.75 | 67500 | Time
5 | 5.46 | Product Deployment | Proceed with installation at rest of Gen1 customer sites | 5.45 | Complete remaining installations using any learnings from the initial installation sites |  |  | 4 | 80 | 320 | Reposit Power | Blended rate | 168.75 | 54000 | Time
5 | 5.45 | Social Research | Use app feedback system and interviews to gather customer experience and sentiment data | 5.45 | After installation is complete, and before cars are utilised, gather customer feedback via social research, and in-app features including override button and real time feedback |  |  | 3 | 60 | 180 | Reposit Power | Blended rate | 168.75 | 30375 | Time
5 | 5.47 | Digital Trust Validation | Internal review of PKI identification and security | 4.43 | Verify security certificate system is functional |  |  | 2 | 40 | 80 | Reposit Power | Blended rate | 168.75 | 13500 | Time
5 | 5.45 | Market Integration | Pass AEMO performance validations, register Gen1 V2G EVSE into FCAS Dispatchable Unit | 5.45 | Enable enrollment in AEMO systems for FCAS |  |  | 4 | 80 | 320 | Reposit Power | Blended rate | 168.75 | 54000 | Time
5 | 5.48 | Market Integration | Enable 5-minute spot price response on Gen1 sites | 5.46 | Ensure that the Gen1 sites are capable to participate in 5-minute spot price trading. Conduct demonstration trial |  |  | 3 | 60 | 180 | Reposit Power | Blended rate | 168.75 | 30375 | Time
5 | 5.45 | Market Integration | Enable dynamic network price response where supported on Gen1 sites. | 5.46 | Where a customer DNSP supports Dynamic Network Prices (i.e Project Edith), V2G chargers will begin responding to these. |  |  | 3 | 60 | 180 | Reposit Power | Blended rate | 168.75 | 30375 | Time
5 | 5.49 | Digital Trust Validation | Penetration testing by 3rd party | 5.47 | Testing to verify the robust implementation of cyber security measures |  |  | 2 | 40 | 80 | External | Blended rate | 168.75 | 13500 | Direct cost
5 | 5.45 | Market Integration | Add Gen1 customers to RERT and/or MSL DUIDs | 5.46 | Ensuring Gen 1 customers can participate in RERT and Minimum system demand events |  |  | 2 | 40 | 80 | Reposit Power | Blended rate | 168.75 | 13500 | Time
| . | [8 empty] | 0 | Reposit Power | Blended rate | 168.75 | 0 | Time
6 | 6.46 | Customer Product Development | Develop & finalise experimental design for validating V2G No Bill product | 5.45 | Develop a 6 month demonstration project trial plan |  |  | 4 | 80 | 320 | Reposit Power | Blended rate | 168.75 | 54000 | Time
6 | 6.47 | Customer Product Development | Gather operational data from Gen1 sites over 6 months | 5.46 | Implement the 6 month trial plan - operational of BEV to test response, availability and customer sentiment |  |  | 26 | 60 | 1560 | Reposit Power | Blended rate | 168.75 | 263250 | Time
6 | 6.48 | Data Collection and Reporting | Produce key data pack (raw data points, overviews of market participation) | 6.47 | Collect and store demonstration project data |  |  | 3 | 60 | 180 | Reposit Power | Blended rate | 168.75 | 30375 | Time
6 | 6.49 | Data Collection and Reporting | Customer Experience Research/Feedback gathering | 4.43 | Collect and compile customer experience feedback during and at conclusion of the project. Data from trial, customer journey and experience, performance reporting, cyber security reporting, lessons learnt and recommendations, including investment decision |  |  | 4 | 80 | 320 | Reposit Power | Blended rate | 168.75 | 54000 | Time
6 | 6.50 | Data Collection and Reporting | Reposit to reach determination on ongoing No Bill V2G offering | 6.47 | Reposit to make investment decision on full product offering of No Bill V2G. |  |  | 2 | 40 | 80 | Reposit Power | Blended rate | 168.75 | 13500 | Time
6 | 6.51 | Data Collection and Reporting | Digital Trust Report, including pentesting results | 5.49 | Compile cyber security report, including recommendations |  |  | 3 | 60 | 180 | Reposit Power | Blended rate | 168.75 | 30375 | Time
6 | 6.52 | Data Collection and Reporting | Produce recommendations report on lessons learnt and advice to industry | 6.47 | Compile lessons learnt and recommendations report |  |  | 30 | 60 | 1800 | Reposit Power | Blended rate | 168.75 | 303750 | Time
other |  | Content development |  |  | Learning Centre content about V2G, V2G in No Bill, V2G EVSE unit and install info, impacts on specific cars [warranty, safety, app, etc, etc] - Comms person - $1k/day - 10 days | 2027-06-01 | 2027-06-11 | 1.8 | 40 | 72 | Reposit | CX designer | 143.75 | 10350 | Time
other |  | Customer Journey |  |  | Customer Journey design to include the the V2G product option - Service Designer - $2k/day - 5 days | 2027-06-01 | 2027-06-11 | 1.8 | 40 | 72 | Reposit | CX designer | 143.75 | 10350 | Time
other |  | Customer Journey |  |  | Customer Journey implementation and testing to include the the V2G product option - Revenue Ops Engineer - $1k/day - 5 days | 2027-06-01 | 2027-06-06 | 0.8 | 40 | 32 | Reposit | CX designer | 143.75 | 4600 | Time
other |  | Customer Application |  |  | Customer App changes to include V2G storage - Senior Developer - $1.5k/day - 20 days | 2027-06-06 | 2027-06-27 | 3 | 40 | 120 | Reposit | Senior Developer | 153.125 | 18375 | Time
other |  | Fleet costs |  |  | Fleet management system changes to incorporate V2G EVSE + Car Models - $1.5k/day - 15 days | 2027-07-01 | 2027-07-15 | 2.2 | 40 | 88 | Reposit | Senior Developer | 153.125 | 13475 | Time
other |  | Hardware development |  |  | Trialog ComboCS with OCPP + ISO 15118-20 |  |  |  |  | 1 |  |  | 34807.5 | 34807.5 | Direct Cost
other |  | Hardware development |  |  | Starcharge Halo 7.4kW (single phase) |  |  |  |  | 5 |  |  | 7000 | 35000 | Direct Cost |  | Customers to pay the bulk, but we probably need to subsidise a bit, and at least 1 or two of these will be "lab" installs, so not customer-bought. Will be between 30 and 50 in the end
other |  | Hardware development |  |  | (maybe) Starcharge Halo 11kW (three phase) |  |  |  |  | 5 |  |  | 10000 | 50000 | Direct Cost |  | Not currently available/being homologated for Australia, but possibly available when installs commence. Price is a guesstimate. Preferred to the single phase for FCAS performance.
other |  | Hardware development |  |  | (maybe) Lab Test Vehicle |  |  |  |  | 1 |  |  | 25000 | 25000 | Direct Cost |  | In case we do need to test on a non-consumer vehicle, we'll likely pick up an Atto 1 for $25k incl all costs
other |  | Hardware development |  |  | Versinetic OCPP2.1 Licenses |  |  |  |  | 1 |  |  | 30000 | 30000 | Direct Cost |  | No idea what Versinetic will charge.
other |  | Develop and publish educational articles for Reposits learning center, and support guides for customer support team |  |  | AEMO PMS (FCAS) Registration Fee |  |  |  |  | 1 |  |  | 3000 | 3000 | Direct Cost
Formulas:
Working weeks in period = INT(NETWORKDAYS([Start],[Finish]))/5

## Labour Rates
Role | Rate Per Day (RPD) | Rate Per Hour (RPH)
Project Manager | 1300 | 162.5
CEO | 2850 | 356.25
CFO | 1900 | 237.5
Senior Developer | 1225 | 153.125
Senior Energy Analyst | 1150 | 143.75
Financial controller | 1224 | 153
Engineering Developer | 1150 | 143.75
CTO | 1900 | 237.5
Project technical lead | 1300 | 162.5
External nil | 0 | 0
Reporting Lead | 1300 | 162.5
CX designer | 1150 | 143.75
Blended rate | 1350 | 168.75

## Pilot Costs
Requirement | Cost | Units
Charger
Car?
Marketing
Software

## Incurred Costs
Item | Est RRP, AUD | Quantity | Total Cost | Notes
Trialog ComboCS with OCPP + ISO15118-20 | 34807.5 | 1 | 34807.5
Starcharge Halo 7.4kW (single phase) | 7000 | 40 | 280000 | Customers to pay the bulk, but we probably need to subsidise a bit, and at least 1 or two of these will be "lab" installs, so not customer-bought. Will be between 30 and 50 in the end
(maybe) Starcharge Halo 11kW (three phase) | 10000 | 10 | 100000 | Not currently available/being homologated for Australia, but possibly available when installs commence. Price is a guesstimate. Preferred to the single phase for FCAS performance.
(maybe) Lab Test Vehicle | 25000 | 1 | 25000 | In case we do need to test on a non-consumer vehicle, we'll likely pick up an Atto 1 for $25k incl all costs
Versinetic OCPP2.1 Licenses | ? | 50 |  | No idea what Versinetic will charge.
AEMO PMS (FCAS) Registration Fee | 3000 | 1 | 3000

## Workshop
WorkStream | Work Activity | Task Name | SUM of Total | Milestone | Outcome | Knowledge sharing
Market Development | Project Initiation | 1. Kickoff meeting and technical review between key technical partners | 16500 | 1 | Finalised project Plan | Lessons learnt on partner perspectives, expected challenges
| DERM Development - Controller | 2. Develop program dispatch and control technical specification | 70000 | 1 | Dispatch and Control specification | Dispatch and control specification
|  | 3. Develop MQTT implementation | 27500 | 1
|  | 4. Develop local OCPP 2.1 implementation | 82500 | 1 | Localised OCPP 2.1 | Description of OCPP2.1 and discussion on localisation recommendations
|  | 5. Develop program value computation strategy and technical requirements | 2340000 | 2 | (How much of this is IP - commercial in confidence) | Progress Report - Lessons learnt, challenges, issues, customer in
|  | 6. Develop and test DERM technical solution | 2340000 | 3 | (How much of this is IP - commercial in confidence) | Progress Report - Lesson learnt and test results
|  | 6. Operate and Maintain DERM technical solution | 0
|  | 7. Release to production environment | 0
| Customer-related works | 8. Develop conceptual customer offering in lieu of BESS at site | 12500 | 1 | Proposed Customer Offer | Customer insights, proposed offer,
|  | 9. Undertake detailed economic study of value potentials (dependent on 1/3 of field trials being completed for existing customers) | 50000 | 1 | High level revenue forefast prediction Market analysis | High level value stacking (not optomised)
|  | 10. Finalise V2G-only customer offering | 12500
|  | 11. Prepare stage 2 trial customer agreement materials | 12500
|  | 12. Legal advice | 40000
|  | 13. Content development about V2G, V2G in No Bill, V2G EVSE unit and install info, impacts on specific cars (warranty, safety, app, etc, etc) | 10000
|  | 14. Customer Journey design to include the the V2G product option | 10000
|  | 15. Customer Journey implementation and testing to include the the V2G product option | 5000
|  | 16. Customer App changes to include V2G storage | 80000
|  | 17. Fleet management system changes to incorporate V2G EVSE + Car Models | 60000
|  | 18. Go to market, acquire 10 V2G-only customers | 45000
|  | 19. Conduct research on protocol learnings for interoperable DERMs in V2G contexts | 60000
|  | 20. Prepare and release report to OCA | 17875
|  | 21. Prepare and release report to CharIN | 17875
| Customer-related works Total |  | 433250
| Knowledge Sharing | 22. Prepare and release report to Standards Australia | 35750
|  | 23. Finalise report on MQTT vs OCPP control | 30000
|  | 24. Finalise report on value sharing | 69000
| Knowledge Sharing Total |  | 134750
| EVSE | 25. Delivery and installation of EVSEs | 0
|  | 26. Develop V2G installation SWMS | 2500
|  | 27. Order and delivery of V2G EVSEs | 6000
|  | 28. Installation of first 20 EVSEs to existing customers | 158400
|  | 29. Installation of last 10 EVSEs to new customers | 79200
|  | 30. V2G VPP trials | 0
|  | 31. EV OEM 1 | 0
|  | 32. VPP live on EV OEM 1 vehicles - existing customers | 65760
|  | 33. VPP live on EV OEM 1 vehicles - new customers | 65760
|  | 34. EV OEM 2 | 0
|  | 35. VPP live on EV OEM 2 vehicles - existing customers | 65760
|  | 36. VPP live on EV OEM 2 vehicles - new customers | 65760
|  | 37. EV OEM 3 | 0
|  | 38. VPP live on EV OEM 3 vehicles - existing customers | 65760
|  | 39. VPP live on EV OEM 3 vehicles - new customers | 65760
|  | 40. EV OEM 4 | 0
|  | 41. VPP live on EV OEM 4 vehicles - existing customers | 65760
|  | 42. VPP live on EV OEM 4 vehicles - new customers | 65760
|  | 43. EV OEM 5 | 0
|  | 44. VPP live on EV OEM 5 vehicles - existing customers | 65760
|  | 45. VPP live on EV OEM 5 vehicles - new customers | 65760
|  | 46. V2G VPP trial closeout | 0
|  | 47. EV OEM 1 cohort | 0
|  | 48. Return phase 1 OEM 1 vehicles to OEM | 1500
|  | 49. Return phase 2 OEM 1 vehicles to OEM | 1500
|  | 50. Transfer phase 1 OEM 1 customers to production code, remove any trial infrastructure | 1500
|  | 51. Transfer phase 2 OEM 1 customers to production code, remove any trial infrastructure | 1500
|  | 52. EV OEM 2 cohort | 0
|  | 53. Return phase 1 OEM 2 vehicles to OEM | 1500
|  | 54. Return phase 2 OEM 2 vehicles to OEM | 1500
|  | 55. Transfer phase 1 OEM 2 customers to production code, remove any trial infrastructure | 1500
|  | 56. Transfer phase 2 OEM 2 customers to production code, remove any trial infrastructure | 1500
|  | 57. EV OEM 3 cohort | 0
|  | 58. Return phase 1 OEM 3 vehicles to OEM | 1500
|  | 59. Return phase 2 OEM 3 vehicles to OEM | 1500
|  | 60. Transfer phase 1 OEM 3 customers to production code, remove any trial infrastructure | 1500
|  | 61. Transfer phase 2 OEM 3 customers to production code, remove any trial infrastructure | 1500
|  | 62. EV OEM 4 cohort | 0
|  | 63. Return phase 1 OEM 4 vehicles to OEM | 1500
|  | 64. Return phase 2 OEM 4 vehicles to OEM | 1500
|  | 65. Transfer phase 1 OEM 4 customers to production code, remove any trial infrastructure | 1500
|  | 66. Transfer phase 2 OEM 4 customers to production code, remove any trial infrastructure | 1500
|  | 67. EV OEM 5 cohort | 0
|  | 68. Return phase 1 OEM 5 vehicles to OEM | 1500
|  | 69. Return phase 2 OEM 5 vehicles to OEM | 1500
|  | 70. Transfer phase 1 OEM 5 customers to production code, remove any trial infrastructure | 1500
|  | 71. Transfer phase 2 OEM 5 customers to production code, remove any trial infrastructure | 1500
|  | 72. Customer trial portion complete | 0
|  | 73. Upgraded gateway metrology for multi-FCAS | 0
|  | 74. Specification and planning | 36000
|  | 75. Design and development | 120000
|  | 76. Prototyping and validation | 60000
|  | 77. Certification and pilot production | 120000
|  | 78. Production ramp up | 100000
| EVSE Total |  | 1369700
Market Development Total |  |  | 6814200
Digital Trust |  | 1. Development of V2G PKI performance targets against Australian and international cybersecurity landscape (internal report for ENA) | 91500 | 1
|  | 2. Consultation on V2G PKI performance targets | 97500
|  | 3. Final reporting on V2G PKI performance targets | 6250
|  | 4. Development of private PKI / test environment processes for ISO 15118-2 | 250
|  | 5. Development of private PKI / test environment processes for ISO 15118-20 | 250
|  | 6. Development of processes to provision and use Hubject APAC PKI in ISO 15118-2 secured charging | 3125
|  | 7. Development of processes to provision and use Hubject APAC PKI in ISO 15118-20 secured charging | 3125
|  | 8. OEM 1 Hubject integration | 17500
|  | 9. OEM 2 Hubject integration | 17500
|  | 10. OEM 3 Hubject integration | 17500
|  | 11. OEM 4 Hubject integration | 17500
|  | 12. OEM 5 Hubject integration | 17500
|  | 13. Development of report detailing PKI processes for secured charging in Australia under ISO 15118-2 and ISO 15118-20 | 159000
|  | 14. Consultation on report detailing PKI processes for secured charging in Australia under ISO 15118-2 and ISO 15118-20 | 75750
|  | 15. Finalisation of report detailing PKI processes for secured charging in Australia under ISO 15118-2 and ISO 15118-20 | 16250
|  | 16. Publishing of report detailing PKI processes for secured charging in Australia under ISO 15118-2 and ISO 15118-20 | 0
|  | 17. Study of proliferation, scalability and implementation requirements of ISO 15118 PKI ecosystems in Australia | 148500
|  | 18. Review of work, key systems and components inherent throughout the project compiled in the context of a study of knowledge, standards gaps and value transferability study for AC V2G | 148500
Digital Trust Total |  |  | 837500
Project Management | Corporate Services | 3. Accounting (blended salary rate) | 157200
|  | 4. Authorship | 117900
|  | 5. Escalation and signoff | 35370
| Corporate Services Total |  | 310470
| PMO | 1. Project Manager | 3537000
| PMO Total |  | 3537000
| Steering Committee | 2. Steering committee particpation | 229905
| Steering Committee Total |  | 229905
Project Management Total |  |  | 4077375
Grand Total |  |  | 11729075