## Gantt Chart
Task ID | Workstream | Task Name | Dependencies | Duration (Wks) | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52 | W53 | W54 | W55 | W56 | W57 | W58 | W59 | W60 | W61
1.1 | Project Initiation | 1. Kickoff meeting and technical review between key technical partners |  | 1 | W1: 1.1
1.2 | Project Initiation | 1. Kickoff meeting and technical review between key technical partners |  | 1 | W1: 1.2
1.3 | Project Initiation | 1. Kickoff meeting and technical review between key technical partners |  | 1 | W1: 1.3
1.4 | Project Initiation | 1. Kickoff meeting and technical review between key technical partners |  | 2 | W1: 1.4
1.5 | Project Initiation | Procure lab testing hardware & development kit. |  | 2 | W1: 1.5
1.6 | Reposit Controller Hardware Enhancement | Design for three additional FCAS-compliant metering channels |  | 1 | W1: 1.6
1.10 | Hardware Communication | Procure EVSE unit for lab testing |  | 1 | W1: 1.10
1.11 | Reposit Cloud Enhancement | Develop configuration tools & database structure for EVSE & Vehicle configuration |  | 5 | W1: 1.11
2.14 | Reposit Controller Software Enhancement | Develop bidirectional EVSE decision-making capabilities |  | 16 | W1: 2.14
2.21 | Customer Product Development | Identify test vehicle (BYD provided, lent or acquired) | 2.2 | 2 | W1: 2.21
3.26 | Customer Product Development | Add key controls (i.e overrides) and data displays to Reposit app |  | 8 | W1: 3.26
3.27 | Customer Product Development | In-App Customer Feedback engine |  | 2 | W1: 3.27
5.45 | Market Integration | Add Gen1 customers to RERT and/or MSL DUIDs | 5.46 | 2 | W1: 5.45
5.46 | Product Deployment | Proceed with installation at rest of Gen1 customer sites | 5.45 | 4 | W1: 5.46
5.48 | Market Integration | Enable 5-minute spot price response on Gen1 sites | 5.46 | 3 | W1: 5.48
6.46 | Customer Product Development | Develop & finalise experimental design for validating V2G No Bill product | 5.45 | 4 | W1: 6.46
6.47 | Customer Product Development | Gather operational data from Gen1 sites over 6 months | 5.46 | 26 | W1: 6.47
6.48 | Data Collection and Reporting | Produce key data pack (raw data points, overviews of market participation) | 6.47 | 3 | W1: 6.48
6.50 | Data Collection and Reporting | Reposit to reach determination on ongoing No Bill V2G offering | 6.47 | 2 | W1: 6.50
6.52 | Data Collection and Reporting | Produce recommendations report on lessons learnt and advice to industry | 6.47 | 30 | W1: 6.52
1.7 | Reposit Controller Hardware Enhancement | Design for new SoC to support 6-channel FCAS metering & disjunctive optimisation | 1.6 | 1 | W2: 1.7
1.8 | Hardware Communication | Finalise ISO 15188-20 specification | 1.1 | 4 | W2: 1.8
1.9 | Hardware Communication | Finalise OCPP2.1 specification | 1.1 | 3 | W2: 1.9
1.12 | Digital Trust Validation | Wireframe PKI specification agreed | 1.1 | 6 | W2: 1.12
1.13 | Market Integration | Engage with DNSPs on connection approval requirements | 1.1 | 6 | W2: 1.13
2.15 | Customer Product Development | Identify existing Reposit customers with potentially compatible vehicles | 1.1 | 2 | W2: 2.15
3.22 | Vehicle Offering Finalisation | Vehicle OEM provides test vehicle(s) and/or firmware version for testing | 2.21 | 1 | W3: 3.22
3.28 | Reposit Controller Hardware Enhancement | Finalise upgraded controller specifications and manufacture prototypes | 1.7 | 20 | W3: 3.28
3.23 | Hardware Communication | Test end-to-end power setpoint response from controller through to vehicle | 3.22 | 8 | W4: 3.23
3.24 | Customer Product Development | Draft customer value proposition for initial No Bill product | 2.15 | 6 | W4: 3.24
4.34 | Vehicle Offering Finalisation | Vehicle OEM produces warranty terms or waivers specifically covering vehicles used within the project | 3.22 | 3 | W4: 4.34
2.16 | Hardware Communication | OCPP 2.1 server implemented on Reposit Controller | 1.9 | 16 | W5: 2.16
2.17 | Hardware Communication | OCPP 2.1 client on EVSE | 1.9 | 14 | W5: 2.17
2.18 | Hardware Communication | Test vehicle and EVSE ISO 15118-20 Communication | 1.8 | 6 | W6: 2.18
3.31 | Reposit Controller Software Enhancement | Develop EV forecast engine (predict connectivity, energy needed for mobility) | 1.11 | 12 | W6: 3.31
4.44 | Market Integration | Get DNSP approvals for Gen1 customer installations | 1.13 | 2 | W8: 4.44
3.25 | Customer Product Development | Test notional product with prospective customers to validate uptake potential | 3.24 | 6 | W10: 3.25
4.35 | Customer Product Development | Employ & on-board customer concierge | 3.24 | 52 | W10: 4.35
4.36 | Customer Product Development | T&C legal review | 3.24 | 2 | W10: 4.36
3.29 | Market Integration | Identify FCAS services which can be delivered via V2G | 3.23 | 4 | W12: 3.29
3.32 | Reposit Controller Software Enhancement | Implement new vehicle & EVSE metric collection and publication to cloud | 3.23 | 6 | W12: 3.32
4.37 | Customer Product Development | Finalise customer V2G product within project | 4.36 | 6 | W12: 4.37
4.40 | Product Deployment | Produce installation instructions, safety guidelines and other key material for installers | 3.23 | 4 | W12: 4.40
3.30 | Reposit Controller Software Enhancement | Enhance frequency response control to enable V2G FCAS delivery | 3.29 | 10 | W16: 3.30
3.33 | Customer Product Development | End-to-end test from Reposit App, through to test vehicle | 3.32 | 4 | W18: 3.33
4.39 | Customer Product Development | Learning Centre expansion & Customer Support Training | 4.37 | 5 | W18: 4.39
4.41 | Product Deployment | Procure EVSE for customer installations | 4.37 | 2 | W18: 4.41
4.42 | Customer Recruitment Marketing | Create and deploy marketing to identify customers for trial | 4.37 | 4 | W18: 4.42
2.19 | Reposit Controller Software Enhancement | Control Schema for EVSE Implemented | 2.16 | 14 | W21: 2.19
2.20 | Hardware Communication | Test end-to-end telemetry from Reposit controller to BEV (notional - actual or mock BEV device) | 2.16, 2.17, 1.10 | 6 | W21: 2.20
4.38 | Customer Product Development | Release updated Reposit App with EVSE+Vehicle support | 3.33 | 8 | W22: 4.38
4.43 | Customer Recruitment Marketing | Recruit Gen1 customers | 4.42 | 3 | W22: 4.43
5.47 | Digital Trust Validation | Internal review of PKI identification and security | 4.43 | 2 | W25: 5.47
6.49 | Data Collection and Reporting | Customer Experience Research/Feedback gathering | 4.43 | 4 | W25: 6.49
5.49 | Digital Trust Validation | Penetration testing by 3rd party | 5.47 | 2 | W27: 5.49
6.51 | Data Collection and Reporting | Digital Trust Report, including pentesting results | 5.49 | 3 | W29: 6.51